## Sheet1
| HREiR Action plan template (January 2021-January 2023) |  |  |  |  | Add institutional logo
Details
| Institution name: | Liverpool John Moores University | The institutional audience* for this action plan includes (complete or delete, as appropriate):
| Cohort number: | 7 | Audience (beneficiaries of the action plan) | Number of | Comments
| Date of submission: | 29.01.2021 | Research staff | 138 | The target cohort for this Concordat is externally funded, fixed-term research staff and our action plan is focused on this audience. We recognise that many other groups will incorporate research activities within their contracts and for whom the Concordat principles will be relevant.
| Institutional context: | Liverpool John Moores University (LJMU) is committed to ensuring that staff are valued and supported to thrive in an environment where personal development and scholarship are central to the delivery of impactful research. LJMU is currently midway through delivery of our 2017-2022 Strategic Plan and through this the University continues to deliver on its ambitions to provide an enabling and facilitative environment for all staff. LJMU have continued to evolve the excellent provision available for researcher development through a variety of programmes offered, including through our Leadership and Development Foundation and our well-established award-winning ACTivator programme. The publication of the revised Researcher Development Concordat in 2019 provided the opportunity for reflection on our previous Concordat progress, resulting in a shift in focus to enable exploration of the specific structural and systemic challenges experienced by researchers on fixed-term contracts. As a result, researchers employed on externally funded fixed-term contracts (n at LJMU = 138) are the target audience for our new Concordat Action Plan (CAP). In line with our shift in focus, we have redressed the balance of our Concordat leadership and simplified our structural and governance arrangements. Where previously a Concordat Task Group provided strategic influence, supported by a Concordat Forum to provide operational support; from 2020 onwards we now have one Concordat Steering Group (CSG) that reports directly to our University Research and Knowledge Exchange Committee (URKEC). Further reflecting this shift, our CSG is now led by a Senior Academic with over ten years’ experience of managing externally funded research staff on fixed-term contracts. CSG membership reflects representation across our target cohort and related stakeholders, whilst comprising many of those involved in our previous Concordat activities; thus ensuring consistency and continuity of processes as we transition into the new 2020 CAP. Our previous Concordat Action Plans and HR Excellence in Research Reviews are available here: https://www.ljmu.ac.uk/about-us/structure/professional-services/research-and-innovation-services/concordat
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result | Action carried over from previous action plan? | Old Concordat principle and clause
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | We will include reference to the Researcher Development Concordat (RDC) within the job description/person specification for fixed-term research posts to state: LJMU are committed to adhering to the Principles set out in the Researcher Development Concordat; in line with this all fixed-term researchers will be supported to complete 10 days professional development activities per year (pro-rata). | Researcher awareness of the RDC to exceed the sector benchmarks (previously measured by CROS [15%] - to be measured using CEDARS). Completion rate for CEDARS to exceed the sector benchmark for CROS (24% in 2017) by achieving 35% completion amongst fixed-term contract researchers. N.B. All actions that incoporate CEDARS will aim to achieve this benchmark. | Job descriptions and person specifications to be updated by April 2021. Implement CEDARS Spring 2021; run again in Spring 2022. | HR responsible for implementation; RDC lead responsible for ensuring CEDARS is implemented. |  |  |  | New
|  | We will include the RDC principles within the LJMU Staff Induction Handbook and Induction sessions. | Our LJMU Staff Induction Handbook and Induction Sessons will include RDC principles. We will measure awareness of this via CEDARS and have set a target that 70% of our target cohort will be aware of the RDC by Spring 2022 (building by 5% year-on-year). | Handbooks to be updated by April 2021. Implement CEDARS Spring 2021; run again in Spring 2022. | HR responsible for implementation; RDC lead responsible for ensuring CEDARS is implemented.
|  | We will develop Research Brochures for all Faculties and include the RDC in here, including reference to the Staff Researcher Assocation (see ECI6). We will also include this information on Faculty webpages. Brochures will highlight the Institutional and Faculty research strategy the individual’s role within that strategy, support and career development opportunities including appraisal. Brochures will advocate for engagement with CEDARS and set-out the University’s commitment to the Principles of the Concordat to Support the Career Development of Researchers. Brochures will also include a statement of expectations for researchers, highlighting the duty to be a supportive colleague. | All Faculties to develop Research Brochures by September 2021. | By Sep 2021 | Associate Deans for Research (ADRs) responsible for implementing and monitoring this action.
|  | We will encourage fixed-term research staff to speak at LJMU Research Cafes throughout the year; this would focus on their research and their experiences at LJMU, with reference to the RDC. | We do not currently collect information about the number of fixed-term staff who speak at our Research Cafes. We will collect this data and review engagement annually, with an expectation that a minimum of 5 fixed-term research staff will present each year (Dec 2021, 2022). We will measure awareness of Research Cafe opportunities via CEDARS. | Implement CEDARS Spring 2021. Review Research Café data annually (Dec 2021 and Dec 2022). | RDC lead and Library Services (organisers of the Research Café) are responsible for implementing and monitoring this action.
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | The development of our Faculty brochures will ensure that policies and practices relevant to researchers are well communicated to researchers and managers. We will cascade information about these brochures through School Directors, research managers and communications materials. | Researchers and managers will have knowledge about the instituitional policies and practicies relevant to researchers, to be measured via the CEDARS survey: a target of 75% of researchers and managers will report awareness of the Faculty brochures and we have set a target that 70% of these will be aware of the RDC by Spring 2022 (building by 5% year-on-year). | Implement CEDARS Spring 2021; run again Spring 2022. | Associate Deans for Research (ADRs), School Directors, research managers responsible for implementing the action; RDC lead responsible for ensuring action is measured. |  |  |  | P2.1 P6.8
|  | LJMU hold the bronze Athena Swan award which requires the institution to develop, implement and monitor inclusive, equitable and transparent policies and practices. We will pursue accreditation for all University schools/departments.We will encourage all STEMM departments to submit Athena applications by April 2022. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). In addition, Liverpool Business School, School of Justice Studies and Liverpool Screen School are all due to submit in April 2021. | April 2021, April 2022 | LJMU’s Athena SWAN Working Group.
|  | An interactive training package is in the process of being developed that addresses Equality, Diversity and Inclusion and will be aimed at researchers (including research leaders and managers) | Pre and post training data will be collected (led by the EDI Manager) to identify immediate changes in knowledge, attitudes and perceptions. Longer-term outcomes will also be captured (all via online surveys). We have no baseline for changes in knowledge, attitudes and perceptions but aim for 50% of research managers and researchers to engage in the training in Year 1 (by September 2022). | Training to be implemented by September 2021. First assessment of engagement /update and changes in attitudes to be measured September 2022. | EDI Manager, LJMU. |  |  |  | P2.1 P6.8
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | LJMU is rolling out a new three-stage strategy to support staff mental wellbeing. The first stage is to provide training for managers.This will help to take team leaders beyond being aware of mental health to being alert to actual situations and to having the confidence and tools to support those in need. The following two stages of the strategy will see the development of new resources to help all LJMU staff and the recruitment of volunteers from the LJMU community to support this key initiative. The strategy is an important part of our efforts to ensure LJMU is a place where staff members with mental health conditions feel supported and are able to thrive. | As a new strategy, there is no benchmark on which to base our success. We hope that within 6 months of roll-out, 40% of research managers will have engaged with the training (to be monitored by HR). Engagement and impact of the training will be measured via HR monitoring of the strategy and the CEDARS survey. | Training to be rolled out across 2021; Implement CEDARS Spring 2021; re-run Spring 2022. | HR responsible for implementing and monitoring the strategy; RDC lead responsible for implementing CEDARS. |  |  |  | P6.9
|  | Our Leadership and Development Foundation (LDF) provide resilience training and time management training, as well as coaching. We will promote this to research leaders and fixed-term contract researchers through our Researcher Associaton (see ECI6) and other promotional RDC activities (e.g. see ECI1). | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). As a minimum we expect 35% of fixed-term staff to engage in these activities, increasing to 50% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS.
|  | Our ACTivator programme provides an 'Attending to You' programme of workshops looking at thinking styles, purpose, confidence, imposter syndrome etc which support the mental wellbeing of academics. We will promote this to research leaders and fixed-term contract researchers through our Researcher Associaton (see ECI6) and other promotional RDC activities (e.g. see ECI1). | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). As a minimum we expect 35% of fixed-term staff to engage in these activities, increasing to 50% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS.
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | LJMU provide online EDI training that staff must complete on an annual basis. All staff are made aware of this when starting with LJMU and the completion of these courses must be confirmed during PDPRs. We will promote this via the RDC promotional activities, described above. | We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards; as this is mandatory we expect all (100%) fixed-term researchers to completed this by Spring 2022. We will also collect pre and post evaluation data to understand the outcomes of these sessions (see action PCDI6). We will further explore awareness and outcomes via CEDARS. | HR to review EDI monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | HR and LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. |  |  |  | P2.3
|  | As, noted in ECI2: An interactive training package is in the process of being developed that addresses Equality, Diversity and Inclusion and will be aimed at researchers (including research leaders and managers). | Pre and post training data will be collected (led by the EDI Manager) to identify immediate changes in knowledge, attitudes and perceptions. Longer-term outcomes will also be captured (all via online surveys). We have no baseline for changes in knowledge, attitudes and perceptions but aim for 50% of research managers and researchers to engage in the training in Year 1 (by September 2022). | Training to be implemented by September 2021. First assessment of engagement/update and changes in attitudes to be measured September 2022. | EDI Manager, LJMU
|  | LJMU hold the bronze Athena Swan award which requires the institution to develop, implement and monitor inclusive, equitable and transparent policies and practices. We will pursue accreditation for all University schools/departments. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). In addition, Liverpool Business School, School of Justice Studies and Liverpool Screen School are all due to submit in April 2021. | Deadline for submissions April 2021, April 2022 | LJMU’s Athena SWAN Working Group
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | This is a requirement of the UK Research Integrity Office. We will provide opportunities to involve fixed-term research staff in policy development and in hearing mock allegations of misconduct. | At least 10% of our Concordat cohort will be engaged in these types of activities per year (not currently measured therefore no benchmark in place). Data will be collected by those responsible for implementing the action (supported by the RDC lead). | Review implementation and participation annually, from Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | Our Research and Knowledge Exchange Committee, Research Excellence Manager and Pro-VC for Research will develop these opportunities, supported by the RDC lead. |  |  |  | P6.1
|  | All new starters will receive an Induction from their Head of Department that will include reference to the LJMU Code of Practice for Research. We will also ensure research staff are aware of the Preventing Harm in Research resource https://www.ukri.org/wp-content/uploads/2020/10/UKRI-050920-PreventingHarmSafeguardingInResearchAndInnovationPolicy.pdf | 100% of new starters to receive an Induction. To be monitored via Staff Infobase and with information collected by HR. Awareness of Code of Practice will also be measured via the CEDARS survey. | Percentage of new starters receiving an induction will be reviewed annually (Dec). CEDARS will be implemented in Spring 2021; re-run 2022. | Research Managers to lead Induction; to be monitored via Staff Infobase (collected by HR). CEDARS to be implemented by RDC lead.
|  | The University has processes in place to address poor practice. We will incorporate Research Integrity into all of the researcher development (e.g. ACTivator) workshops as a common thread that runs throughout; the content will be shaped by the fixed-term researchers (via the Researcher Association (see ECI6). | Research Integrity to be incorporated into our researcher development activities by the LDF (e.g. ACTivator). There is no baseline to measure success but we would expect 35% of the Concordat cohort to attend during Year 1 (aligned with other action plan targets). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Research Integrity to be incorporated into our researcher development activities by the LDF by September 2021. Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | The LDF to incorporate Research Integrity into researcher development activities, and collect satisfaction and outcomes data annually. CEDARS to be implemented by RDC lead.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | All schools/departments will hold staff away days where groups can discuss and feed back to Director/Heads of Department. These away days will be supported by the LDF who will encourage academic teams to design events that are meaningful and which elicit useful outcomes. | 70% of Schools/Departments to report holding away days by December 2021, with a target for 100% of Schools/Departments to have held one away day by Spring 2022. Puposeful planning and outcomes will be reported at each respective Faculty Management Team (FMT) meeting. We will also explore staff experiences/outcomes of this via CEDARS, (but would not expect this to be captured in the Spring 2021 round). | By Spring 2022, each School/ Department will have held one away day, with plans to implement this on an annual basis. Away day information to be reported to FMT, and reported to Research and Knowledge Exchange Committee by Associate Deans for Research (ADRs). Implement CEDARS Spring 2021; re-run 2022. | ADRs to support each Faculty to implement, monitor via FMT and report to the Research and Knowledge Exchange Committee. CEDARS to be implemented by RDC lead. |  |  |  | P6.10 P7.5
|  | Research leaders within schools/departments will be responsible for holding quarterly meetings to provide opportunity for research group leaders to contribute to discussions on department, Faculty and Institutional strategy. The minutes of these meetings will be fed into the department Management Team (which will subsequently be fed into FMTs and our Research and Knowledge Exchange Committee). | 70% of Schools/Departments to report holding Research Leaders meetings, to be captured in the FMT meeting minutes. We will also explore staff experiences/ outcomes of this via CEDARS, but we would not expect this to be captured in the Spring 2021 round. | By Spring 2022, each School/ Department will hold quarterly Research Leader meetings; information to be reported to FMT, and reported to Research and Knowledge Exchange Committee by Associate Deans for Research (ADRs). Implement CEDARS Spring 2021; re-run 2022. | ADRs to support each Faculty to implement. RDC Lead to support with monitoring progress.
|  | Develop a Researcher Association, led on a voluntary basis by researchers, with the aim of contributing to Institutional policy and practice development and developing best practice. The Association will feed in to the Concordat Steering Group, which reports directly to the URKEC. | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Staff will report active engagement in this group; engagement with Institutional policy and practice development will be collected by the RDC lead and measured via anonymous annual evaluation (online survey). | By Sep 2021 | RDC Lead.
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | [7 empty] | P6.6
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers | [7 empty] | New
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions | [7 empty] | P6.6
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | Managers of researchers must complete all mandatory training on an annual basis. All staff are made aware of this when starting with LJMU and the completion of these courses must be confirmed during appraisals. | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of fixed-term research staff who engage with mandatory training but will collect this data going forwards (see action PCDI6). As a minimum we expect 70% of fixed-term staff to engage in mandatory training, increasing to 85% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. |  |  |  | New
|  | Following ECI2: Research managers must engage with the interactive training package that is in the process of being developed that addresses Equality, Diversity and Inclusion and will be aimed at researchers (including research leaders and managers). | Pre and post training data will be collected (led by the EDI Manager) to identify immediate changes in knowledge, attitudes and perceptions. Longer-term outcomes will also be captured (all via online surveys). We have no baseline for changes in knowledge, attitudes and perceptions but aim for 50% of research managers and researchers to engage in the training in Year 1 (by September 2022). | Training to be implemented by September 2021. First assessment of engagement /update and changes in attitudes to be measured September 2022. | EDI Manager, LJMU
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | Following ECI5: All research managers must engage with the Research Integrity activities that are being developed. This includes ensuring awaress and understanding of the Preventing Harm in Research resource and actions to address Poor Practice. | Research Managers to engage with training activities regarding Integrity which will be incorporated into our researcher development activities by the LDF (e.g. ACTivator). There is no baseline to measure success but we would expect 35% of Research Managers to attend/engage with Integrity Training during Year 1 (aligned with other action plan targets). We do not collect specific data on the numbers of research managers who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Research Integrity to be incorporated into our researcher development activities by the LDF by September 2021. Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | The LDF to incorporate Research Integrity into researcher development activities, and collect satisfaction and outcomes data annually. CEDARS to be implemented by RDC lead. |  |  |  | New
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | Following ECI3: Our Leadership and Development Foundation (LDF) provide resilience training and time management training, as well as coaching. Research managers will be expected to attend and complete this training, and protect time for the researchers whom they manage to attend. | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of research managers who engage with LDF activities but will collect this data going forwards (see action PCDI6). As a minimum we expect 35% of fixed-term staff to engage in these activities, increasing to 50% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Departments, Faculty ADRs to promote these activities to research managers. LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. |  |  |  | P6.9
|  | Following ECI3: Our ACTivator programme provides an 'Attending to You' programme of workshops looking at thinking styles, purpose, confidence, imposter syndrome etc which support the mental wellbeing of academics. Research managers will be expected to discuss these during research appraisals and protect time for researchers to attend, should they wish. | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of research managers who engage with LDF activities but will collect this data going forwards (see action PCDI6). As a minimum we expect 35% of fixed-term staff to engage in these activities, increasing to 50% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Departments, Faculty ADRs and Research managers to promote these activites to research managers. LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS.
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | LJMU have been actively pursuing this action, specifically through the bronze Athena Swan award, and our work towards Silver, which requires the institution to develop, implement and monitor inclusive, equitable and transparent policies and practices. Flexible working requests and actions to support Research Managers to consider these requests form part of this process. In order to further develop this we will pursue Athena Swan accreditation for all University schools/departments (as detailed in ECI1). | We will collect data specific to our RDC cohort and use this as a benchmark in 2021, to improve performance in 2022. | Review the views of all staff, in terms of feasibility, on an annual basis via Athena Swan reporting processes (collect views annually from Dec 2021). Implement CEDARS Spring 2021; re-run Spring 2022. | Heads of Schools/ Department Faculty ADRs and Research managers to promote Athena Swan goals. Athena Swan Working Group responsible for coordinating this. RDC Lead responsible for implementing CEDARS |  |  |  | New
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | At school/departmental level, research managers are expected to engage with (and/or lead) research leader meetings, aimed to enable research leaders to contribute to relevant policy and strategy discussions, influencing at research institute and institutional level. Meetings will be held quarterly and minutes will be provided to the management team within the relevant school/department, which will in turn be reported to FMT. | 70% of Schools/Departments to report holding Research Leader meetings, to be captured in the FMT meeting minutes. We will also explore staff experiences/ outcomes of this via CEDARS, but we would not expect this to be captured in the Spring 2021 round. | By Spring 2022, each School/ Department will hold quarterly Research Leader meetings; information to be reported to FMT, and reported to Research and Knowledge Exchange Committee by Associate Deans for Research (ADRs). Implement CEDARS Spring 2021; re-run 2022. | ADRs to support each Faculty to implement. RDC Lead to support with monitoring progress. |  |  |  | New
|  | Research managers will support and encourage fixed-term researchers to become actively involved in the Research Staff Association (developed as part of objective ECI6). | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Awareness of these opportunities, feasibility of allowing researchers to take part in this and the outcomes of engagement will be measured via anonymous annual evaluation (online survey). | Review annually, Dec 2021. Implement CEDARS Spring 2021, re-run 2022. | RDC Lead responsible for developing the Researcher Association and implementing monitoring to measure success. Research managers to support their staff to attend, if they wish.
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | Researchers must complete all mandatory training on an annual basis. All staff are made aware of this when starting with LJMU and the completion of these courses must be confirmed during appraisals. | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of fixed-term research staff who engage with mandatory training but will collect this data going forwards (see action PCDI6). As a minimum we expect 70% of fixed-term staff to engage in mandatory training, increasing to 85% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. |  |  |  | New
|  | Following ECI2 and ECM1: Researchers must engage with the interactive training package that is in the process of being developed that addresses Equality, Diversity and Inclusion. | Pre and post training data will be collected (led by the EDI Manager) to identify immediate changes in knowledge, attitudes and perceptions. Longer-term outcomes will also be captured (all via online surveys). We have no baseline for changes in knowledge, attitudes and perceptions but aim for 50% of research managers and researchers to engage in the training in Year 1 (by September 2022). | Training to be implemented by September 2021. First assessment of engagement /update and changes in attitudes to be measured September 2022. | EDI Manager, LJMU
|  | Following ECM4: Researchers will be encouraged to join the Researcher Association. | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Awareness of these opportunities, feasibility of allowing researchers to take part in this and the outcomes of engagement will be measured via anonymous annual evaluation (online survey). | Review annually, Dec 2021. Implement CEDARS Spring 2021. | Research managers and fixed-term researchers to advocate. RDC Lead to set up the group and monitor progress.
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | Researchers must read the Faculty research handbook [ECI1] and complete all mandatory modules. | 100% of research staff must complete the mandatory modules. Staff awareness and experiences will continue to be monitored using CEDARS and the results using to continually inform activities. | Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Department Faculty ADRs and Research managers to promote. RDC lead responsible for ensuring CEDARS is implemented. |  |  |  | P5.3
|  | Following ECI5: All researchers must engage with the Research Integrity activities that are being developed. This includes ensuring awaress and understanding of the Preventing Harm in Research resource and actions to address Poor Practice. | Researchers to engage with training activities regarding Integrity which will be incorporated into our researcher development activities by the LDF (e.g. ACTivator). There is no baseline to measure success but we would expect 35% of researchers to attend/engage with Integrity Training during Year 1 (aligned with other action plan targets). We do not collect specific data on the numbers of research managers who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Research Integrity to be incorporated into our researcher development activities by the LDF by September 2021. Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | The LDF to incorporate Research Integrity into researcher development activities, and collect satisfaction and outcomes data annually. Research Managers to promote this to staff. CEDARS to be implemented by RDC lead.
ECR3 | Take positive action towards maintaining their wellbeing and mental health | Following ECI3: Researchers will be encouraged to make use of the staff mental health/wellbeing support available and report to their line manager any issues relating to workload at the earliest opportunity, rather than wait for their appraisal. | Numbers of fixed-term research staff attending these activities will be measured. There is no baseline to measure success but we expect 90% of staff will report feeling confident to report issues to line managers and to make use of LJMU support services. This will be measured via CEDARS. | Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Department LDF and Research managers to promote and support mental wellbeing. CEDARS to be implemented by RDC lead. |  |  |  | New
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | LJMU have specific mechanisms in place to ensure researchers (all staff) can report any harassment, bullying, research misconduct or discriminatory behaviour. In line with ECI5, this will be better promoted to researchers. Researchers will be expected to attend ACTivator workshops that include sessions on research integrity (to be developed as part of action ECI5). | We have no baseline on which to measure change, but we expect that 75% of researchers will report that they are aware of the mechanisms by which they can report any harassment, bullying, research misconduct or discriminatory behaviour (in Spring 2021). We want to build on this to achieve 85% awareness by Spring 2022. This evidence will be collected via CEDARS. | Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Department LDF and Research managers to promote and support mental wellbeing. CEDARS to be implemented by RDC lead. |  |  |  | P6.9
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | In line with objective ECI6, researchers will be encouraged to attend the Researcher Association. This will provide the mechanism for staff to actively contribute to discussions relating to policies and processes. | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Awareness of these opportunities, feasibility of allowing researchers to take part in this and the outcomes of engagement will be measured via anonymous annual evaluation (online survey). | Review annually, Dec 2021. Implement CEDARS Spring 2021. | Research managers and fixed-term researchers to advocate. RDC Lead to set up the group and monitor progress. |  |  |  | P3.13
|  | Researchers are provided with the opportunity to take part in University-wide initiatives, including this Concordat Steering Group and Athena Swan, for example. | Concordat cohort engagement with these activities will be measured through Committee membership. We would expect at least one fixed-term research staff member to be represented across key University-wide initiatives. Staff will report opportunities to engage with initiatives within the CEDARS (alongside their experiences and outcomes of this engagement). We have no baseline, but would expect 60% of staff to report awareness of opportunities to engage within the Spring 2021 CEDARS survey. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | Research managers and fixed-term researchers to advocate. RDC Lead to set up the group and monitor progress.
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | Action links with ECI4: LJMU holds the Bronze Athena Swan award which requires the institution to develop, implement and monitor open, transparent and merit-based recruitment. We are working towards our Silver award and will pursue accreditation for all University schools/departments. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). | Deadline for submissions April 2021, April 2022 | LJMU’s Athena SWAN Working Group |  |  |  | P1.2 P6.2 P6.7
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | Builds on action ECI1: All staff should receive a Staff Induction which includes receiving an induction handbook that provides details about the RDC. | Previous: We had previously measured the number of staff engaging with Inductions on a 3-yearly basis. Our data for all academic staff suggests that 62.5% of staff have had an Induction. Data specific to staff on fixed-term contracts is not collected, although this will be addressed as part of our action plan (e.g. through actions ECI1 and ECI5) and we have a target that 70% of fixed-term research staff will receive an induction by the end of 2021, rising to 85% by December 2022. | HR to monitor the numbers of Inductions taking place. | HR responsible for implementation and monitoring. |  |  |  | P3.6
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | Links to action ECI1: As part of the development of the Faculty Brochures, we will include information about the institutional and local research strategy, the individual’s role within that strategy, support and career development opportunities including appraisal. Handbooks will advocate for engagement with CEDARS and set out the University’s commitment to the Principles of the Concordat to Support the Career Development of Researchers. | Completion rate for CEDARS to exceedt the sector benchmark for CROS (24% in 2017) by achieving 35% completion amongst fixed-term contract researchers. | Handbooks to be updated by April 2021. Implement CEDARS Spring 2021; run again in Spring 2022. | HR responsible for implementation; RDC lead responsible for ensuring CEDARS is implemented. |  |  |  | P2.6 P6.3 P6.4 P6.7
|  | Links to action ECI4: LJMU holds the Bronze Athena Swan award which requires the institution to develop, implement and monitor open, transparent and merit-based recruitment. We are working towards our Silver award and will pursue accreditation for all University schools/departments | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). | Deadline for submissions April 2021, April 2022 | LJMU’s Athena SWAN Working Group
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | LJMU offer specific training for line managers and project managers through LDF and the ACTivator programme, however the issue of fixed-term researchers (and others) not having research-experienced line management is a big issue in many parts of the University. As well as ensuring all line managers complete the mandatory modules, we will prioritise fixed-term researchers for mentorship, so they have an experienced mentor in addition to their line manager to support their career development, progresion and wellbeing. | Our data show that we have an extensive mentorship programme in place, however we do not collect data specifically regarding externally funded fixed-term researchers. We therefore have no benchmark for success, but expect that a minimum of 10 fixed-term researchers have a dedicated mentor to focus on career development, progression and wellbeing. We would want this to raise to 20 by Spring 2022. | Implement CEDARS Spring 2021; run again in Spring 2022. | LDF are responsible for implementing, promoting and monitoring uptake of training; RDC Lead is responsible for implementing CEDARS. |  |  |  | P2.3
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | Action links with ECI4: LJMU holds the bronze Athena Swan award which requires the institution to develop, implement and monitor people management processes. We will pursue accreditation for all University schools/departments. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). | Deadline for submissions April 2021, April 2022 | LJMU’s Athena SWAN Working Group |  |  |  | P2.6 P6.3 P6.4
|  | Equal opportunities data will be collected about promotion and specific actions taken to increase awareness of this route amongst research managers and fixed-term researchers. | Staff satisfaction with people management will be measured through CEDARS. 70% of fixed-term researchers will demonstrate satisfaction when CEDARS runs in 2022. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | HR
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | A review (baseline) of staff on fixed-term contracts is currently underway and will be completed during the implementation of this current action plan. The review is exploring the numbers of staff of fixed-term contracts, and characteristics including numbers of fixed-term staff, retention and redeployment figures. | The results and implications of the review will be completed during 2021 and the findings reported by the RDC Lead to LJMU's Executive Leadership Team and used to inform specific actions which we anticipate to include methods to reduce reliance on short-term rolling contracts. | Actions to be formed and implemented by Dec 2021. | Head of Contracts, HR leading the review. |  |  |  | P1.3 P2.1 P2.2
|  | We will use the information from the review to develop actions to reduce reliance on short-term fixed-term contracts. The Concordat, EDI and Race Charter will provide our catalysts for change. This will provide the opportunity to gain a cross-University view of available resource. | Success will include improved levels of mental wellbeing and productivity as measured by HR data (retention, sickness) and through CEDARS; we will collect a baseline for this amongst the RDC cohort via CEDARS in Spring 2021 and aim to a 10-20% improvement on this by the 2022 survey. | Implement CEDARS Spring 2021; re-run 2022. | Head of Contracts, HR, RDC Lead to implement and monitor this action.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | Following ECI6: We will develop a Researcher Association, led on a voluntary basis by researchers, with the aim of contributing to Institutional policy and practice development and developing best practice. The Association will feed in to the Concordat Steering Group, which reports directly to the URKEC. | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Staff will report active engagement in this group; engagement with Institutional policy and practice development will be collected by the RDC lead and measured via anonymous annual evaluation (online survey). | By Sep 2021 | RDC Lead. |  |  |  | P3.13
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies | [7 empty] | P2.4
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security | [7 empty] | New
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression | [7 empty] | P2.4
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels | [7 empty] | New
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | Researcher managers must complete all mandatory LJMU training modules. We will explore optimal ways to identify research managers so that we can monitor these activities. At present, our LJMU HR systems are quite devolved so we need to engage with HR at Institutional level to enable us to monitor this. Research managers will also be encouraged through RDC promotional activities (e.g. ECI1) to participate in wider ACTivator and LDF training. | 100% of research staff must complete the mandatory modules. Staff awareness and experiences will continue to be monitored using CEDARS and the results using to continually inform activities. | Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Department Faculty ADRs and Research managers to promote. RDC lead responsible for ensuring CEDARS is implemented. |  |  |  | P2.3
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and Codes of Practice, institutional policies, and the terms and conditions of grant funding | In line with ECI1, research managers must familiarise themselves with the Faculty Brochure and materials that provide details about our Codes of Practice. | We have no baseline on which to measure success but we would expect 70% of research managers to demonstrate awareness of the RDC, to be measured via the CEDARS survey. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | Research managers responsible for engaging with materials; HR responsible for implementation; RDC lead responsible for ensuring CEDARS is implemented. |  |  |  | P2.2
|  | Following ECI5: The University has processes in place to incorporate Research Integrity into all of the researcher development (e.g. ACTivator) workshops as a common thread that runs throughout; the content will be shaped by the fixed-term researchers (via the Researcher Association (see ECI6). | Research Integrity to be incorporated into our researcher development activities by the LDF (e.g. ACTivator). There is no baseline to measure success but we would expect 35% of the Concordat cohort to attend during Year 1 (aligned with other action plan targets). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Research Integrity to be incorporated into our researcher development activities by the LDF by September 2021. Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | Research managers responsible for engaging with training. The LDF to incorporate Research Integrity into researcher development activities, and collect satisfaction and outcomes data annually. CEDARS to be implemented by RDC lead.
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | Research managers must engage will all LJMU EDI training, including that is outlined within objective EI5. This training covers specific modules on recruitment, promotion and rewards. This also includes aspects specific to Athena Swan and the Race Charter highlighted across this action plan (e.g. EI6). | Progress against this will be measured through a range of actions related to this e.g. ECI5 (Athena Swan). Staff satisfaction with people management will be measured through CEDARS. 70% of fixed-term researchers will demonstrate satisfaction when CEDARS runs in 2022. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | HR and EDI are responsible for implementing actions related to the Race Charter. The RDC Lead will implement monitoring processes. |  |  |  | P6.3
|  | The Vitae Researcher Development Framework (RDF) offers structure for research managers to use during appraisals (although is not appropriate for all subjects). The use of this framework will be advocated to research managers during line management training and promoted by LDF. | Use (and associated expected/actual) outcomes of the Vitae RDF will be explored via Appraisals. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | LDF, research managers
|  | Promotion of fixed-term research staff through Readership and Professorship will be tracked. This data is not currently collected for fixed-term research staff. | We will collect data specific to our RDC cohort and use this as a benchmark in 2021, to improve performance in 2022. We will explore staff awareness of opportunities to apply for this route via CEDARS and attendance at progression events (e.g. 110 academic staff attended our most recent progression event; specific data will be collected related to the Concordat cohort). | Review annually Dec 20201 and Dec 2022. | HR to collate data, RDC Lead to implement monitoring data.
|  | Relates to Action ECI5: LJMU hold the bronze Athena Swan award which requires the institution to develop, implement and monitor inclusive, equitable and transparent policies and practices. We will pursue accreditation for all University schools/departments. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). | Deadline for submissions April 2021, April 2022 | LJMU’s Athena SWAN Working Group
EM4 | Actively engage in regular constructive performance management with their researchers | Research managers should hold regular 1-1 meetings with researchers to discuss issues relating to wellbeing, workload and performanced. This is more formally monitored through the PDPR. | 100% of staff should have a PDPR. Staff engagement in 1-1s and the effectiveness and satisfaction of this will be explored within CEDARS. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | HR and research managers to promote and implement appraisals, HR to monitor, RDC Lead to implement CEDARS. |  |  |  | P2.3
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | Following action ECI6: Research managers within schools/departments will be responsible for engaging in quarterly research leader meetings to provide opportunity for research group leaders to contribute to discussions on department, Faculty and Institutional strategy. The minutes of these meetings will be fed into the department Management Team (which will subsequently be fed into FMTs and our Research and Knowledge Exchange Committee). | 70% of Schools/Departments to report holding Research Leaders meetings, to be captured in the FMT meeting minutes. We will also explore staff experiences/ outcomes of this via CEDARS, but we would not expect this to be captured in the Spring 2021 round. | By Spring 2022, each School/ Department will hold quarterly Research Leader meetings; information to be reported to FMT, and reported to Research and Knowledge Exchange Committee by Associate Deans for Research (ADRs). Implement CEDARS Spring 2021; re-run 2022. | ADRs to support each Faculty to implement. RDC Lead to support with monitoring progress. |  |  |  | New
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | Following ECI5: All researchers must engage in research integrity training and support that is offered. | There will be no benchmark to measure success but we would expect 50% of the Concordat cohort to attend during Year 1. Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | EDI, Research managers |  |  |  | New
ER2 | Understand their reporting obligations and responsibilities | This obligation links into the actions which are addressed within Action ECI5 relating to research integrity. | Research Integrity to be incorporated into our researcher development activities by the LDF (e.g. ACTivator). There is no baseline to measure success but we would expect 35% of the Concordat cohort to attend during Year 1 (aligned with other action plan targets). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Research Integrity to be incorporated into our researcher development activities by the LDF by September 2021. Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | The LDF to incorporate Research Integrity into researcher development activities, and collect satisfaction and outcomes data annually. CEDARS to be implemented by RDC lead. |  |  |  | New
ER3 | Positively engage with performance management discussions and reviews with their managers | All researchers are expected to participate in 1-1s and appraisals. Further, researchers are expected to engage with the relevant LDF and ACTivator programmes/workshops and consider ways to implement this learning to shape their performance. | 100% of staff should have an appraisal. Staff engagement in 1-1s and the effectiveness and satisfaction of this will be explored within CEDARS with a target that 80% of staff will report feeling that they have opportunities to discuss performance management. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022.. | School Directors and Research managers responsible for ensuring appraisals take place. RDC Lead responsible for monitoring this activity. |  |  |  | P5.6
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | In line with objective ECI6, researchers will be encouraged to attend the Researcher Association. This will provide the mechanism for staff to actively contribute to discussions relating to policies and processes. | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Staff will report active engagement in this group; engagement with Institutional policy and practice development will be collected by the RDC lead and measured via anonymous annual evaluation (online survey). | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022.. | RDC Lead to implement. |  |  |  | P5.2
|  | Researchers are provided with the opportunity to take part in University-wide initiatives, including this Concordat Steering Group and Athena Swan, for example. | 75% of staff on fixed-term contracts will report having opportunity to participate in activities that influence and feed into University-wide initiatives; 35% will report participating in such activities by Dec 2021. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022.. | Research managers to provide support; RDC Lead to monitor and implement CEDARS. |  |  |  | P5.2
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | We will include reference to the Researcher Development Concordat (RDC) within the job description/person specification for fixed-term research posts to state: LJMU are committed to adhering to the Principles set out in the Researcher Development Concordat; in line with this all fixed-term researchers will be supported to complete 10 days professional development activities per year (pro-rata). | Success: we would expect this to be included in all induction materials/contracts by April 2021. 100% of staff to report discussing this in July 2021 appraisals. | Implement by April 2021, and review progress and outcomes Dec 2021 and Dec 2022 via appraisal information. | HR to implement and collect monitoring data. |  |  |  | P3.1 P3.3 P5.5
|  | All research managers and researchers wll be expected to discuss and plan opportunities for these activities during appraisals and in regular 1-1 meetings. | We have no benchmark, but would expect researchers to engage with a mimimum requirement of 5 days by the end of Year 1, building to 8 by by the end of Year 2. This information would be collected during appraisals and using the CEDARS survey. | Review progress and outcomes Dec 2021 and Dec 2022 via appraisal information. | School Directors; Research managers to implement and review; RDC Lead to monitor.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | LJMU provide an e-learning module for all managers 'Appraisals and Connected Conversations'. We will promote this to managers of fixed-term research staff via School Directors, appraisals and our promotional materials (and to aspiring research managers through the Researcher Association). We will promote this through School Directors and our handbooks (Concordat materials), collect data about the awareness and effectiveness of this via appraisals, CEDARS and through the collection of data specific to our Concordat cohort. | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). As a minimum we expect 35% of fixed-term staff to engage in these activities, increasing to 50% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | HR, LDF |  |  |  | P3.10
|  | Develop a process that easily identifies those managers of fixed-term research staff so that they can be prompted (by HR) to fulfill their responsibilities here, and provide high quality information and/or sign-posting.This will be used by research leaders, ADRs and other relevant staff to identify research capacity across the University. | By September 2021, we will have a comprehensive overview of managers of fixed-term staff. 75% of researc h leaders will report knowledge of this, to be reviewed through HR recruitment process and via CEDARS. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | HR
|  | A number of staff in our Leadership Development Foundation are qualified coaches and offer 1:1 coaching in conducting and preparing for appraisals. We will offer coaching training to all managers of fixed-term research staff and promote this via School Directors. We will promote this to School Directors, appraisals and our promotional materials (and to aspiring research managers through the Researcher Association). | We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated with a target of 90% satisfaction (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey, with 70% of staff reporting awareness by April 2022. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | HR, LDF
|  | The Vitae Wheel offers structure for research managers to use during appraisals. The use of this wheel will be advocated to research managers during line management training and promoted by LDF. | Use (and associated expected/actual) outcomes of the Vitae wheel will be explored via Appraisals. 70% of researchers will report using the wheel, where applicable, via apprasial reviews. This will also be explored via CEDARS. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | LDF, research managers
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | Our Leadership and Development Foundation (LDF) have a dedicated website that provides information about all training that is offered. In line with objective PCDI6, we will collect information specific to the Concordat Cohort. | We have no benchmark to assess the % of fixed-term contract researchers who engage with LDF training but will start to collect this (see objective PCDI6) and expect to see a 30% increase between Dec 2021 and Dec 2022. | Review annually, Dec 2021 and Dec 2022. | Research managers |  |  |  | P3.1
|  | LDF will pilot a 'Being Leadership' series of workshops which will focus on communications, empathy and self-awareness. This will be promoted to fixed-term research staff by promotional materials, School Directors and research managers. | We will collect implementation and outcomes data on the pilot. We will explore attendance, awareness and outcomes via this process and also via CEDARS. | Pilot Feb 2021; implement CEDARS Spring 2021 | LDF
|  | Wider development opportunities will be cascaded via our central LJMU communications team and via the Researcher Association. | 75% of staff will recall seeing staff development opportunities via communications (e.g. emails, newsletters) as captured via CEDARS in 2022. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | LDF and LJMU Communications Team
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | Our Leadership and Development Foundation (LDF) and ACTivator workshops provide opportunities for research staff to develop identity and leadership skills. The engagement of fixed-term research staff will be supported via action PCDI1. In line with objective PCDI6, we will collect information specific to the Concordat Cohort. | Success: we would expect fixed-term research staff to engage with a minimum 5 days professional development activity that includes activity to develop research identity and leadership skills. Outcomes will be collected via CEDARS survey and appraisals. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | LDF, research managers |  |  |  | P3.11 P3.14
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | We will commit to exploring the development of an interactive workshop for employers/researchers to liaise with employers to provide job opportunities. We are aware of examples across the sector (e.g. University of Liverpool's Prosper Workshop) and will learn from these to explore the possibiltiy of developing a bespoke workshop for our research community, with a focus on fixed-term researchers. | The development and delivery of a workshop with attendance from at least 40% of staff on fixed-term research contracts. Experiences of this will be captured via pre and post monitoring and engagement with attendees. | April 2022. | Pro-VC Research, LDF |  |  |  | P3.2 P3.4
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | Our ACTivator programme is constantly reviewed and adapted to address emerging needs e.g. the development of the new ‘Being Leadership’ series of workshops has been prompted by feedback from researchers. We will target fixed-term research staff with these activities via the promotional methods described elsewhere (e.g. PCDI1, ECI1) and by implementing data collection measures specific to this cohort. | Attendance by fixed-term research staff at core ACTivator workshops will increase from 16% to 20% (based on overall attendance rates). We will also explore the effectiveness and awareness about these programmes via CEDARS. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | Research managers, fixed-term researchers. |  |  |  | New
|  | ACTivator (and LDF) data is currently collected by gender, Faculty, School and other broad information. We are in the process of adding an indicator to enable us to collect data on contract type. This will enable us to identify progress specific to our Concordat cohort. | Data collection measures will be embedded by April 2021. | 2021-04-01 | Concordat Steering Group Lead to liaise with LDF/HR. |  |  |  | New
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning | [7 empty] | P3.7 P3.9
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes | [7 empty] | New
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit | [7 empty] | New
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | Managers of fixed-term research staff will be encouraged to discuss this during appraisals. Whilst this (and the LDF/ACTivator programme) are encouraged, this will be actively promoted through the Concordat materials. | 100% of staff should have an appraisal. Fixed-term research staff engagement in these and the effectiveness and satisfaction of this will be explored within CEDARS. | Review annually, Dec 2021 and Dec 2022. | Research Managers |  |  |  | P2.3
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | We will deliver, evaluate and review the ACTivator programme with specific promotion to the managers of fixed-term research staff. This will include data specific to the Concordat cohort (see Action PCD16). We will engage research managers with CEDARS in 2021 to explore implementation and outcome data. | Increased researcher engagement with development activities, specifically core ACTivator workshops with 75% of research managers and fixed-term research staff attending at least one workshop per academic year (there is no current benchmark specifically for this cohort). No benchmark for CEDARS completion but previous CROS survey was 24%; we will aim for 35% completion. | Implement CEDARS Spring 2021 (to run on a two-yearly basis). | LDF, School Directors, Research Managers |  |  |  | P3.4 P3.8 P5.5
|  | Fixed-term research staff will be assigned a mentor as part of their Induction process. LDF offer a matching service for existing fixed-term research staff that will be promoted to research managers via School Directors and through Concordat promotion activities (described elsewhere in this action plan). | Success: all new contract research staff will be assigned a mentor. To be measured through the induction process and also via CEDARS. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | HR, LDF, Research Managers
|  | LJMU will are planning to be involved in a pilot led by Salford University for cross-institutional mentoring. Opportunities for fixed-term research staff to engage with this will be promoted via LDF, School Directors and through Concordat promotion activities (described elsewhere in this action plan). | The pilot project will be evaluated and if successful will be rolled out by December 2022. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | LDF
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | Research managers must commit to allowing their staff to engage in the minimum 10 days pro rata and plan this into their resource and project plans accordingly. | We have no benchmark, but would expect researchers to engage with a mimimum requirement of 5 days by the end of Year 1, building to 8 by by the end of Year 2. This information would be collected during appraisals (line manager monitoring) and using the CEDARS survey. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | School Directors; Research managers |  |  |  | New
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | Research managers will discuss fixed-term research staff development requirements during regular 1-1s and appraisals. Research managers will familiarise themselves with LDF and ACTivator programmes (as a minimum) with specific training requirements (e.g. research skills) identified and acted upon via appraisals. | Increased researcher engagement with development activities, specifically core ACTivator workshops with 75% of research managers and fixed-term research staff attending at least one workshop per academic year (there is no current benchmark specifically for this cohort). | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | School Directors; Research managers |  |  |  | P3.6 P3.9 P5.5
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | Ensure the Concordat cohort are engaged with LJMU provision for future research leaders: the Research Team Leadership programme. Deliver, evaluate and review leadership development provision for future research leaders, Engage staff with CEDARS in 2021 and develop an associated action plan. | A minimum of one cohort annually of fixed-term research staff (n=10) to complete the ‘Research Team Leadership programme’. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | School Directors; Research managers |  |  |  | New
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | Fixed-term research staff will familiarise themselves with the professional development opportunities available to them and actively identify how to engage with the minimum 10-days (pro-rata); this should be discussed at appraisals with specific reference to professional and career development goals. | We have no benchmark, but would expect researchers to engage with a mimimum requirement of 5 days by the end of Year 1, building to 8 by by the end of Year 2. This information would be collected during appraisals (line manager monitoring) and using the CEDARS survey. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | School Directors; Research managers |  |  |  | P5.5
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | Fixed-term research staff will engage with LDF and ACTivator opportunities and actively engage with their mentors. | In line with PCDI6, we will collect data specific to fixed-term research staff to monitor engagement with the LDF and ACTivator provision that is available to staff. We will collect outcomes data through tailored evaluations. We will use CEDARS to collect awareness and impact data. | Review LDF and ACTivator data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Research managers, fixed-term researchers. |  |  |  | P3.8
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | Enusre LJMU Symplectic database is up to date. Consider and develop professional career development plan through appraisals and the use of the Vitae Wheel. | 100% of staff to have an appraisal. 100% of staff will report Sympletic being up to date. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Fixed-term researchers |  |  |  | P5.5
PCDR4 | Positively engage in career development reviews with their managers | Appraisals provide opportunity to discuss this. All fixed-term research staff to prepare and discuss this meaningfully during appraisals. | 100% of staff to have an appraisal and 60% to cite having meaningful discussions regarding career progressions. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Fixed-term researchers |  |  |  | P3.10
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | Commit to engaging with LDF and ACTivator programmes to develop research identity and leadership skills. | Awareness and engagement data will be collected by LDF (following implementation of action PCDI6) and will also be measured via CEDARS. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Fixed-term researchers |  |  |  | P5.5
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | Continue to run the University’s annual Research & Innovation showcase event with a renewed focus on the following objectives: Grow participation (internal, including contract researchers, and external) Re-design the format and content to facilitate an increased emphasis on learning/development outcomes Involve the Concordat Steering Group in the design, planning and running of the event Establish robust measures to evaluate outcomes and satisfaction | No benchmark for Concordat cohort (fixed-term research staff), but based on previous projections aim to increase participation to 25%. We will also implement robust evaluation to identify the outcomes of engagement for researchers and their managers. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Fixed-term researchers |  |  |  | P5.2
|  | Explore the numbers of externally funded research staff applying for Professor and Reader conferment and compare this against the data collected for all applications (and analyse in relation to demographic and other characteristics). | We will continue to monitor our application, shortlisting and award numbers and take remedial action if the proportion of eligible candidates applying for Readership promotion falls below 3% for female staff and 6% for males. We do not have a benchmark for the numbers of Professor and Reader conferment applications by contract type, but will collect this and explore awareness/accessibility of this route by externally funded fixed-term staff (e.g. through staff survey, Spring 2021). | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Concordat Steering Group Lead, HR |  |  |  | P5.2
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional suport staff; technicians.