## Sheet1
| HREiR Action plan template (January 2021-January 2023) |  |  |  |  | Add institutional logo
Details
| Institution name: | Liverpool John Moores University | The institutional audience* for this action plan includes (complete or delete, as appropriate):
| Cohort number: | 7 | Audience (beneficiaries of the action plan) | Number of | Comments
| Date of submission: | 29.01.2021 | Research staff | 138 | The target cohort for this Concordat is externally funded, fixed-term research staff and our action plan is focused on this audience. We recognise that many other groups will incorporate research activities within their contracts and for whom the Concordat principles will be relevant.
| Institutional context: | Liverpool John Moores University (LJMU) is committed to ensuring that staff are valued and supported to thrive in an environment where personal development and scholarship are central to the delivery of impactful research. LJMU is currently midway through delivery of our 2017-2022 Strategic Plan and through this the University continues to deliver on its ambitions to provide an enabling and facilitative environment for all staff. LJMU have continued to evolve the excellent provision available for researcher development through a variety of programmes offered and coordinated through our Leadership and Development Foundation and our well-established award-winning ACTivator programme. The publication of the revised Researcher Development Concordat in 2019 provided the opportunity for reflection on our previous Concordat progress. This resulted in a shift in focus to enable exploration of the specific structural and systemic challenges experienced by researchers on fixed-term contracts. Consequently, researchers employed on externally funded fixed-term contracts (n = 138) are the target audience for our new Concordat Action Plan (CAP). In line with our shift in focus, we have redressed the balance of our Concordat leadership and simplified our structural and governance arrangements. Where previously a Concordat Task Group provided strategic influence, supported by a Concordat Forum to provide operational support; from 2020 onwards we now have one Concordat Steering Group (CSG) that reports directly to our University Research and Knowledge Exchange Committee (URKEC). Further reflecting this shift, our CSG is now led by a Senior Academic with over ten years’ experience of managing externally funded research staff on fixed-term contracts. CSG membership reflects representation across our target cohort and related stakeholders, whilst comprising many of those involved in our previous Concordat activities; thus ensuring consistency and continuity of processes as we transition into the new 2020 CAP. Our previous Concordat Action Plans and HR Excellence in Research Reviews are available here: https://www.ljmu.ac.uk/about-us/structure/professional-services/research-and-innovation-services/concordat
Column1 | Obligation2 | Action | Success Meaure (SMART) | Deadline | Responsibility | Progress upadate (to be completed for submission) | Outcome/result | Column2 | Column3
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | We will include reference to the Researcher Development Concordat (RDC) within the job description/person specification for fixed-term research posts to state: LJMU are committed to adhering to the Principles set out in the Researcher Development Concordat; in line with this all fixed-term researchers will be supported to complete 10 days professional development activities per year (pro-rata).Our Concordat governance processes involve reporting to our URKEC, Executive Leadership Team and Faculty Associate Dean's for Research which will further strengthen awareness of the RDC and action plan. | Researcher awareness of the RDC to exceed the sector benchmarks (previously measured by CROS [15%] - to be measured using CEDARS). Completion rate for CEDARS to exceed the sector benchmark for CROS (24% in 2017) by achieving 35% completion amongst fixed-term contract researchers. N.B. All actions that incorporate CEDARS will aim to achieve this benchmark. | Job descriptions and person specifications to be updated by April 2021. Implement CEDARS Spring 2021; run again in Spring 2022. | HR responsible for implementation; RDC lead responsible for ensuring CEDARS is implemented. | The statement "LJMU are committed to adhering to the Principles set out in the Researcher Development Concordat; in line with this all fixed-term researchers will be supported to complete 10 days professional development activities per year (pro-rata)" has been added to our template FTR job descriptions/person specs and also the template confirmation of employment letters. This statement is now requested to be included in all relevant job descriptions. A small number of inconsistencies in use of this statement have been identified, therefore a future action will be to incorporate this in a HR systems check to minimise non-inclusion of this statement. 52% of all respondents to CEDARS had either some understanding of the RDC [22%], or knew of its existence but did not know all detail [30%]. 59% of FTRs who responded to CEDARS had either some understanding of the RDC [36%] or had heard of it but did not know all the detail [23%]. | This statement has been implemented by means of recommendations, a formal HR check will be considered in a forward facing action plan.
|  | We will include the RDC principles within the LJMU Staff Induction Handbook and Induction sessions. | Our LJMU Staff Induction Handbook and Induction Sessions will include RDC principles. We will measure awareness of this via CEDARS and have set a target that 70% of our target cohort will be aware of the RDC by Spring 2022 (building by 5% year-on-year). | Handbooks to be updated by April 2021. Implement CEDARS Spring 2021; run again in Spring 2022. | HR responsible for implementation; RDC lead responsible for ensuring CEDARS is implemented. | All new starter staff including research staff, are provided with information about LJMU support via joiners pack. 52% of all respondents to CEDARS had either some understanding of the RDC [22%], or knew of it's existence but did not know all detail [30%]. 59% of FTRs who responded to CEDARS had either some understanding of the RDC [36%] or had heard of it but did not know all the detail [23%]. | This information is provided in an LJMU joiners pack. However, we have not achieved the metrics stated as a success measure. The induction process will be further evolved to discuss these principles rather than just cite the text in induction packs.
|  | We will develop Research Brochures for all Faculties and incorporate details pertaining to the RDC in here, including reference to the Staff Researcher Association (see ECI6). We will also include this information on Faculty webpages. Brochures will highlight the Institutional and Faculty research strategy the individual’s role within that strategy, support and career development opportunities including annual appraisal. Brochures will advocate for engagement with CEDARS and set-out the University’s commitment to the Principles of the RDC. Brochures will also include a statement of expectations for researchers, highlighting the duty to be a supportive colleague. | All Faculties to develop Research Brochures by September 2021. | By Sep 2021 | Associate Deans for Research (ADRs) responsible for implementing and monitoring this action. | We have broken down this progress update, by Faculty- information for which was sought directly from School directors. (i) Arts, Professional and Social Studies- This faculty provide an annual ‘sway’ which sets out the years planned research activities and events. Research brochures exist for each of the Research institutes and centres. Research banners and posters which are displayed at faculty , university and public events. (ii) Health - The Public Health Institute (PHI) have a research brochure but the Faculty does not. (iii) Faculty of Engineering & Technology - this Faculty do not have a research handbook, but are currently developing one. (iv) Faculty of Business & Law - This Faculty do not have a research brochure but do have research webpages that contain this information. (v) Faculty of Science - The Faculty of Science has a Research Brochure (Faculty Research Guide) that describes the research infrastructure, policies and related faculty teams and staff and includes information on support for research and support for ECRs (typically through seedcorn funding for new staff at their start of their academic careers). The faculty webpages also contain information on research including research groups and importantly, PhD students belonging to different research groups and centres/institutes. | Collectively, these updates suggest different methods of implementation of this action and thus a degree of inconsistency across the Institution. Our forward facing action plan will therefore strive to roll out a consistent approach across Faculties/Research Institutes.
|  | We will encourage fixed-term research staff to speak at LJMU Research Cafes and Research and Knowledge Exchange events throughout the year; this would focus on their research and their experiences at LJMU, with reference to the RDC. This will also act as an awareness raising mechanism for PGRs and other research staff who may not be aware of the RDC. | We do not currently collect information about the number of fixed-term staff who speak at our Research Cafes. We will collect this data and review engagement annually, with an expectation that a minimum of 5 fixed-term research staff will present each year (Dec 2021, 2022). We will measure awareness of Research Cafe opportunities via CEDARS. | Implement CEDARS Spring 2021. Review Research Café data annually (Dec 2021 and Dec 2022). | RDC lead and Library Services (organisers of the Research Café) are responsible for implementing and monitoring this action. | Between January 2021 and December 2022 Library Services hosted 10 Research Cafes, with a total of 28 speakers. Of these speakers, 19 were PGRs, 4 were academic/lecturing staff, 3 were research staff, and 2 were Professional Services staff. Since the start of 2020/21, Library Services have been actively seeking more speakers at an early stage of their careers (rather than senior academics) but it has been easier to recruit PGRs than RS, because of the relative size of the PGR and RS communities, and because communication channels for reaching PGRs are more established. | Library services now collect and house this data, which is shared with the CSG. Participation of RS at these sessions has been successful and future actions, including the development of a Researcher Association, will facilitate communications with the researcher community in LJMU.
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | The development of our Faculty brochures will ensure that policies and practices relevant to researchers are well communicated to both researchers and their managers/Principal Investigators. Brochure distribution will be cascaded through School Directors, research managers and communications materials. | Researchers and managers will have knowledge about the institutional policies and practices relevant to researchers, to be measured via the CEDARS survey: a target of 75% of researchers and managers will report awareness of the Faculty brochures and we have set a target that 70% of these will be aware of the RDC by Spring 2022 (building by 5% year-on-year). | Implement CEDARS Spring 2021; run again Spring 2022. | Associate Deans for Research (ADRs), School Directors, research managers responsible for implementing the action; RDC lead responsible for ensuring action is measured. | In relation to EC1(iii), brochures, online sways and/or webpages have been developed across some of the research institutes but there appears to be an inconsistent approach across the institution. Reporting on this action has, helpfully, highlighted this; and will inform a future action to apply consistency across research institutes and/or Faculties. | Collectively, these updates suggest different methods of implementation of this action and thus a degree of inconsistency across the Institution. Our forward facing action plan will therefore strive to roll out a consistent approach across Faculties/Research Institutes.
|  | LJMU are committed to our work regarding the Race Equality Charter and also hold a Bronze Institutional Athena Swan Equality Charter award which requires the institution to deliver an action plan which includes the development, implementation and monitoring of inclusive, equitable and transparent policies and practices. LJMU are actively pursuing schools/department level awards by highlighting Institutional EDI aspirations. One department have successfully attained this award (Sports Science) and we will encourage all STEMM departments to submit Athena SWAN applications by April 2022. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). In addition, Liverpool Business School, School of Justice Studies and Liverpool Screen School are all due to submit in April 2021. | April 2021, April 2022 | LJMU’s Athena SWAN Working Group. | The School of Pharmacy and Biomedical Sciences was Awarded an Athena SWAN Bronze Award in 2021, and the final department in the Faculty of Science (School of Biological and Environmental Sciences) was awarded Bronze status earlier in 2022. Other Schools; LJMU Business School and the Astrophysics Research Institute have also been successful in securing Bronze awards. The School of Sport and Exercise Sciences is now preparing for a Silver submission and LJMU is preparing to submit a Silver Institutional Award. LJMU was awarded a Race Equality Charter Bronze Award in 2022 and, at the time, was one of only 24 Universities to hold the Award. | All Faculty of Sciences Schools now have Athena SWAN Bronze awards, as well as the LJMU Business School and the Astrophysics Research Institute
|  | An interactive training package that addresses Equality, Diversity and Inclusion is currently under development and specifically aimed at researchers (including research leaders and managers). | Pre and post training data will be collected (led by the EDI Manager) to identify immediate changes in knowledge, attitudes and perceptions. Longer-term outcomes will also be captured (all via online surveys). We have no baseline for changes in knowledge, attitudes and perceptions but aim for 50% of research managers and researchers to engage in the training in Year 1 (by September 2022). | Training to be implemented by September 2021. First assessment of engagement /update and changes in attitudes to be measured September 2022. | EDI Manager, LJMU. | Research staff are instructed in the mandatory modules alongside all other staff groups, this data can be reported on for Diversity in the workplace. FTRs are respectively compliant at 74%, whilst Research Staff (including KTPs) are at 76% compliant. General Academic staff are at 80%. We have been hosting and reviewing the EDI mandatory training (online), via EDI canvas page, and the in-person / Teams training as per the needs of the institution. Collecting feedback via staff networks, teams and anonymous surveys regarding what colleagues would like to see and in what format. We also design workshops specific to staff teams and students, including Customer Services (Reception), Libraries, COO & Registrar Away Day, PGRs, Student Officers, Course Reps and Student Committees. We also work with speakers with lived experiences and recommend these for colleagues across the institution. All of this work ensures our LJMU community is informed, and there is space for conversations about EDI and shared learning. From CEDARS respondents, 42% all respondents participated in EDI training and 37% RS. Of course, we can't discount the impact that the pandemic has had on training and development delivery, which many colleagues expressed in CEDARs, to have been 'deprioritised' as a result of unprecedented time pressures (family/home and work related). | The provision of training packages has been vastly expanded and the introduction of training in relation to principles of EDI also aligns with our Athena SWAN initiatives. We hope to continue to increase research manager engagement, as indicated in our forward facing action plan.
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | LJMU is rolling out a new three-stage strategy to support staff mental wellbeing. The first stage is to provide training for managers. This will enable managers to be alert to mental health situations and to have the confidence and tools to support those in need. The following two stages of the strategy will see the development of new resources to help all LJMU staff, and the recruitment of volunteers from the LJMU community to support this key initiative. The strategy is an important part of our efforts to ensure LJMU is a place where staff members with mental health conditions feel supported and are able to thrive. | As a new strategy, there is no benchmark on which to base our success. We hope that within six months of roll-out, 40% of research managers will have engaged with the training (to be monitored by HR). Engagement and impact of the training will be measured via HR monitoring of the strategy and the CEDARS survey. We will also measure this by Department, as this information will also be of benefit to the Departmental Athena Swan applications. | Training to be rolled out across 2021; Implement CEDARS Spring 2021; re-run Spring 2022. | HR responsible for implementing and monitoring the strategy; RDC lead responsible for implementing CEDARS. | All stages of this action have been successfully rolled out in LJMU and CEDARS was conducted Summer 2022, which is later than planned. However, CEDARS reveals that 62% of all respondents do not feel they have sufficient time to engage with CPD, and 25% have engaged in no CPD in the last 12months; this is similar in RS, 55% of which expressed they do not have time for CPD, however 67% completed 1-10 CPD activities over the past 12months. This action will be, in part, rolled forward to completion in 2023. | Analysis of the findings of CEDARS is currently taking place which will inform future provision
|  | Our Leadership and Development Foundation (LDF) provide resilience training and time management training, as well as coaching. We will promote this to research leaders and fixed-term contract researchers through our Researcher Association (see ECI6) and other promotional RDC activities (e.g. see ECI1). | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). As a minimum we expect 35% of fixed-term staff to engage in these activities, increasing to 50% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. | According to our CEDARS data, between 30-50% of al respondents and RS reported either having completed or having a desire to complete various workshops hosted by LDF. From our attendance records, a total of 686 staff (n=485 academic, n=129 FTR) attended all ACTivator workshops across 2021, with a further 244 (n=162 academic, n=63 research) during 2022 - due to staff long-term sickness and a review of this programme less sessions ran in 2022. According to our ACTivator evaluation, almost all respondents (n=25, 96.2%) thought that their participation in the ACTivator workshops was a good use of their time. Of the 134 workshops attended by the 26 individuals, 159 benefits were reported (this included individuals attending multiple workshops and reported multiple impacts across the workshops). This ranged from 1-23 impacts (mean impacts n=6). Awareness of funding opportunities (n=15) was the most reported impact, followed by level of confidence (n=11) and knowledge or collection of research impact (n=10). | We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS 2023.
|  | Our ACTivator programme provides an 'Attending to You' programme of workshops looking at thinking styles, purpose, confidence and imposter syndrome, all of which support the mental wellbeing of academics. We will promote this to research leaders and fixed-term contract researchers through our Researcher Association (see ECI6) and other promotional RDC activities (e.g. see ECI1). | We currently collect data on the number of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but do so going forwards (see action PCDI6). As a minimum we expect 35% of fixed-term staff to engage in these activities, increasing to 50% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. | The pandemic also impacted these goals, with colleagues reacting to an ever changing and demanding landscape of personal and professional challenges and time pressures. In 2021 n=111 staff attending the "Attending to You" workshops of which n=65 were academic colleagues and n=28 were FTRs. In 2022, these figures reduced to n=39 (total), n=22 (academic) and n=5, respectively. This suite of development activities have been paused due to a combination of staff sickness and a review of the programmes. The pandemic changed the way our staff accessed training and we are therefore also reviewing our delivery modes, and offering a variety of avenues to engage with development training. | Action in progress, and thus rolled forward
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | LJMU provide online EDI training that staff must complete on an annual basis. All staff are made aware of this when starting with LJMU and the completion of these courses must be confirmed during annual appraisals. We will promote this via the RDC promotional activities, described above. | We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will do so going forwards; as this is mandatory we expect all (100%) fixed-term researchers to completed this by Spring 2022. We will also collect pre and post evaluation data to understand the outcomes of these sessions (see action PCDI6). We will further explore awareness and outcomes via CEDARS. | HR to review EDI monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | HR and LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. | The data is regularly collected and reviewed. The pandemic changed the way our staff accessed training and we are therefore also reviewing our delivery modes, and offering a variety of avenues to engage with EDI. | There is now an attendance monitoring mechanism in place.
|  | As, noted in ECI2: An interactive training package is in the process of being developed that addresses Equality, Diversity and Inclusion and will be aimed at researchers (including research leaders and managers). | Pre and post training data will be collected (led by the EDI Manager) to identify immediate changes in knowledge, attitudes and perceptions. Longer-term outcomes will also be captured (all via online surveys). We have no baseline for changes in knowledge, attitudes and perceptions but aim for 50% of research managers and researchers to engage in the training in Year 1 (by September 2022). | Training to be implemented by September 2021. First assessment of engagement/update and changes in attitudes to be measured September 2022. | EDI Manager, LJMU | Research staff are instructed in the mandatory modules alongside all other staff groups, this data can be reported on for Diversity in the workplace. FTRs are respectively compliant at 74%, whilst Research Staff (including KTPs) are at 76% compliant. General Academic staff are at 80%. Our training offering is regularly shared with staff network, Operations Managers, JMSU Staff and more. We have produced video campaigns titled "Just Ask" and "Getting it Right" to identify immediate reactions. This has helped us capture what protected characteristic there is a lower understanding of and to review our offering accordingly. From CEDARS respondents, 42% all respondents participated in EDI training and 37% RS. | There has been good progress with this action, but awareness can still be enhanced.
|  | LJMU hold a Bronze Institutional Athena Swan Equality Charter award which requires the institution to deliver an action plan which includes the development, implementation and monitoring of inclusive, equitable and transparent policies and practices. LJMU are actively pursuing schools/department level awards by highlighting Institutional EDI aspirations. One department have successfully attained this award (Sports Science) and we will encourage all STEMM departments to submit Athena SWAN applications by April 2022. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). In addition, Liverpool Business School, School of Justice Studies and Liverpool Screen School are all due to submit in April 2021. | Deadline for submissions April 2021, April 2022 | LJMU’s Athena SWAN Working Group | The School of Pharmacy and Biomedical Sciences was Awarded an Athena SWAN Bronze Award in 2021, and the final department in the Faculty of Science (School of Biological and Environmental Sciences) was awarded Bronze status earlier in 2022. Other Schools; LJMU Business School and the Astrophysics Research Institute have also been successful in securing Bronze awards. The School of Sport and Exercise Sciences is now preparing for a Silver submission and LJMU is preparing to submit a Silver Institutional Award. LJMU was awarded a Race Equality Charter Bronze Award in 2022 and, at the time, was one of only 24 Universities to hold the Award. | All Faculty of Sciences School snow have Athena SWAN Bronze awards, as well as the LJMU Business School and the Astrophysics Research Institute
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | This is a requirement of the UK Research Integrity Office. We will provide opportunities to involve fixed-term research staff in policy development and in hearing mock allegations of misconduct. | At least 10% of our Concordat cohort will be engaged in these types of activities per year (not currently measured therefore no benchmark in place). Data will be collected by those responsible for implementing the action (supported by the RDC lead). | Review implementation and participation annually, from Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | Our Research and Knowledge Exchange Committee, Research Excellence Manager and Pro-VC for Research will develop these opportunities, supported by the RDC lead. | Library Services training on aspects of research integrity attracts a mix of people although they don’t know the precise profile of attendees as it’s not something they ask on registration: “Ready Steady Publish” has run 7 times since January 2020 with an average of 10 people attending, more staff than PGRs attending. “Demystifying data” has run 4 times in the last two years typically averaging 6-7 people and again mostly staff. 42% CEDARS respondents had completed training in research integrity with further interest in undertaking training by 47 individuals (34%). | Forward action to coordinate LDF workshops on research integrity and misconduct to try and target researchers more. Library services run workshops on good publications and data management.
|  | All new starters will receive an Induction from their Head of Department that will include reference to the LJMU Code of Practice for Research. We will also ensure research staff are aware of the Preventing Harm in Research resource https://www.ukri.org/wp-content/uploads/2020/10/UKRI-050920-PreventingHarmSafeguardingInResearchAndInnovationPolicy.pdf | 100% of new starters to receive an Induction. To be monitored via Staff Infobase and with information collected by HR. Awareness of Code of Practice will also be measured via the CEDARS survey. | Percentage of new starters receiving an induction will be reviewed annually (Dec). CEDARS will be implemented in Spring 2021; re-run 2022. | Heads of Departments and Research Managers to lead Induction; to be monitored via Staff Infobase (collected by HR). CEDARS to be implemented by RDC lead. | All new starter staff including research staff, should be provided with information about LJMU support via joiners pack. Appraisal completion data for FTC is as follows: 2020 - 11.2%; 2021 - 30.2% and 2022 - 13.1% (these figures are derived from the number of appraisals that were uploaded to the Staff Infobase system). From all respondent to CEDARS; 38% of FTR respondents found their inductions useful to current role and Faculty/Department but only 7% found this useful at Institutional level. These data could be skewed by no-response from 80%. 59% of FTRs who responded to CEDARS had either some understanding of the RDC [36%] or had heard of it but did not know all the detail [23%]. | Forward actions will focus on the recording of FTR induction via staff InfoBase.
|  | The University has processes in place to address poor practice. We will incorporate Research Integrity into all of the researcher development (e.g. ACTivator) workshops as a common thread that runs throughout; the content will be shaped by the fixed-term researchers (via the Researcher Association (see ECI6). | Research Integrity to be incorporated into our researcher development activities by the LDF (e.g. ACTivator). There is no baseline to measure success but we would expect 35% of the Concordat cohort to attend during Year 1 (aligned with other action plan targets). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Research Integrity to be incorporated into our researcher development activities by the LDF by September 2021. Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | The LDF to incorporate Research Integrity into researcher development activities, and collect satisfaction and outcomes data annually. CEDARS to be implemented by RDC lead. | The data is regularly collected and reviewed. The pandemic changed the way our staff accessed training and we are therefore also reviewing our delivery modes. The CEDARS data reveals that 10% all respondents completed research integrity training as did 15% RS. Research integrity workshops were not conducted by LDF, but aspects of research integrity were woven into existing content. LJMU also have an annual research misconduct report, produced by the head of research excellence, and this has received no reports in the last 2 year cycle. | Due to changes in engagement and delivery brought about by the pandemic, the suite of development activity is currently under review and thus this will result in an evolved action for 2023 onwards.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | All schools/departments will hold staff away days where groups can discuss and feed back to Director/Heads of Department. These away days will be supported by the LDF who will encourage academic teams to design events that are meaningful and which elicit useful outcomes. | 70% of Schools/Departments to report holding away days by December 2021, with a target for 100% of Schools/Departments to have held one away day by Spring 2022. Purposeful planning and outcomes will be reported at each respective Faculty Management Team (FMT) meeting. We will also explore staff experiences/outcomes of this via CEDARS, (but would not expect this to be captured in the Spring 2021 round). | By Spring 2022, each School/ Department will have held one away day, with plans to implement this on an annual basis. Away day information to be reported to FMT, and reported to Research and Knowledge Exchange Committee by Associate Deans for Research (ADRs). Implement CEDARS Spring 2021; re-run 2022. | ADRs to support each Faculty to implement, monitor via FMT and report to the Research and Knowledge Exchange Committee. CEDARS to be implemented by RDC lead. | We have broken down this progress update, by Faculty- information for which was sought directly from School directors. (i) Arts, Professional and Social Studies- a strategic research planning day was held in 2022, with another scheduled for 2023; as well as a research centre and institute directors retreat (2days) offsite. (ii) Health - historically held an annual research away day but one has not occurred since the pandemic. (iii) Faculty of Engineering & Technology - this Faculty have not held a research away day since the pandemic but research institutes (BEST, CEBE) DO plan on holding one later in 2023 (iv) Faculty of Business & Law - no away days in 2020 or 2021 due to the pandemic and later the creation of a new team of professors and readers however the Schools have held writing days/retreats and bootcamps. (v) Faculty of Science - all Schools in the Faculty of Science reported having research away days, even if virtual during periods of lockdown. Specifically, all the Research Institutes and Centres in the Faculty (centres/institutes have university biennial reviews) have regular meetings at least quarterly (e.g. the RISES Board comprising all RGLs meets quarterly with minutes and action points produced). Research groups (as opposed to centres/institutes) are not subject to biennial reviews and meet informally, at various times during the year including during research away days. | Deprioritised moving forward as this is focussed on all staff with research responsibilities and not focussed on FTRs.
|  | Research leaders within schools/departments will be responsible for holding quarterly meetings to provide opportunity for research group leaders to contribute to discussions on department, Faculty and Institutional strategy. The minutes of these meetings will be fed into the department Management Team (which will subsequently be fed into FMTs and our Research and Knowledge Exchange Committee). | 70% of Schools/Departments to report holding Research Leaders meetings, to be captured in the FMT meeting minutes. We will also explore staff experiences/ outcomes of this via CEDARS, but we would not expect this to be captured in the Spring 2021 round. | By Spring 2022, each School/ Department will hold quarterly Research Leader meetings; information to be reported to FMT, and reported to Research and Knowledge Exchange Committee by Associate Deans for Research (ADRs). Implement CEDARS Spring 2021; re-run 2022. | ADRs to support each Faculty to implement. RDC Lead to support with monitoring progress. | We have broken down this progress update, by Faculty- information for which was sought directly from School directors. (i) Arts, Professional and Social Studies- . (ii) Health - ADR leads the only research centre in NAP (LCCS). Regular meetings with individual teams throughout 2021-22 but more recently have organised fortnightly centre meetings to discuss applications and collaborations. The centre reports through the IHR which meets regularly and via NAP SMT. ADR also manages all the research active staff in NAP and meet on a monthly basis to discus their ideas and support needed. (iii) Faculty of Engineering & Technology - ARI has had its own regular meetings. Other groups within FET may not have regular formal meetings but individual groups do have informal meetings regularly (e.g. LOOM and DSRC). (iv) Faculty of Business & Law - Regular research group meetings throughout the Faculty, but activity varies in terms of frequency A template has recently been created for quarterly meetings. (v) Faculty of Science - Regular meetings at Institute and group level reported across all Schools in the Faculty of Science. Research Centres and Institutes (official university structures subject to biennial reviews) meet regularly and at least quarterly and I cite the example of RISES, but research groups in RISES and in the other Schools are ‘unofficial’ structures so they meet informally. | Deprioritised moving forward as this is focussed on all staff with research responsibilities and not focussed on FTRs.
|  | Develop a Researcher Association, led on a voluntary basis by researchers, with the aim of contributing to Institutional policy and practice development and developing best practice. The Association will feed in to the Concordat Steering Group, which reports directly to the URKEC. | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Staff will report active engagement in this group; engagement with Institutional policy and practice development will be collected by the RDC lead and measured via anonymous annual evaluation (online survey). | By Sep 2021 | RDC Lead. | LJMU's organisation development manager and the RDC interim lead have held meetings with local institutions who have successfully set up and coordinate research staff associations. The development of this is currently underway, with support from these two key stakeholders. A proposal has been reviewed and approved by URKEC and all FTRs will be automatically added to the RSA in January 2023. A call for chairs and co-chairs will be released simultaneously, with the aspiration of a co-chair per Faculty that can also provide FTR representation at strategic research meetings. | This action has been prioritised moving forwards and will act as a primary mechanism for engaging with the target group. LDF's organisational development manager has therefore joined the CSG.
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | Managers of researchers must complete all mandatory training on an annual basis. All staff are made aware of this when starting with LJMU and the completion of these courses must be confirmed during appraisals. | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of fixed-term research staff who engage with mandatory training but will collect this data going forwards (see action PCDI6). As a minimum we expect 70% of fixed-term staff to engage in mandatory training, increasing to 85% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. | The completion rates for mandatory training for FTRs as at 20th Jan 2023 were: Bribery Act 72%; Diversity in the Workplace 74%; Prevent 58% and Modern Slavery 79%. These data are available through the LJMU LearnUpon portal, reports can be filtered via staff group and role to analyse completion rates. CEDARS data reveals an appetite for more CPD with all respondents and RS expressing a desire to participate in CPD/training activities across all areas, that averaged 20%. | Three of the four mandatory modules have been completed by FTRs to the rate stated in our success measure. That said, we will continue to build on this moving forwards, as reflected in our forward facing action plan. Further, evaluation will be built in to understand the perceived value of these. All comms primarily via RSA.
|  | Following ECI2: Research managers must engage with the interactive training package that is in the process of being developed that addresses Equality, Diversity and Inclusion and will be aimed at researchers (including research leaders and managers). | Pre and post training data will be collected (led by the EDI Manager) to identify immediate changes in knowledge, attitudes and perceptions. Longer-term outcomes will also be captured (all via online surveys). We have no baseline for changes in knowledge, attitudes and perceptions but aim for 50% of research managers and researchers to engage in the training in Year 1 (by September 2022). | Training to be implemented by September 2021. First assessment of engagement /update and changes in attitudes to be measured September 2022. | EDI Manager, LJMU | Research staff are instructed in the mandatory modules alongside all other staff groups, this data can be reported on for Diversity in the workplace. FTRs are respectively compliant at 74%, whilst Research Staff (including KTPs) are at 76% compliant. General Academic staff are at 80%. CEDARs data indicate that 15% of all respondents participated in EDI training, as did 26% RS. A further 10% all respondents and 15% RS expressed a desire to complete this in the future. | These success measures have been achieved, but this action will continue to be prioritised for both FTRs and RMs.
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | Following ECI5: All research managers must engage with the Research Integrity activities that are being developed. This includes ensuring awareness and understanding of the Preventing Harm in Research resource and actions to address Poor Practice. | Research Managers to engage with training activities regarding Integrity which will be incorporated into our researcher development activities by the LDF (e.g. ACTivator). There is no baseline to measure success but we would expect 35% of Research Managers to attend/engage with Integrity Training during Year 1 (aligned with other action plan targets). We do not collect specific data on the numbers of research managers who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Research Integrity to be incorporated into our researcher development activities by the LDF by September 2021. Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | The LDF to incorporate Research Integrity into researcher development activities, and collect satisfaction and outcomes data annually. CEDARS to be implemented by RDC lead. | Attendance and completion records are now collected and available via the Libcal development system. n=26 staff completed the survey assessing satisfaction and outcomes- the majority of those who had engaged in the survey being on open-ended (permanent and core-funded) contracts (n=18, 69.2%). Smaller proportions on were on fixed term (n=6, 23.1%) and externally funded contracts (n=1, 3.8%), and one person (3.8%) was unsure of their contract type. 7 interviews semi-structured interviews were conducted with; Research fellow, Reader, Associate director, Research funding coordinator, Senior lecturer, PhD researcher, Professor. From our attendance records, a total of 686 staff (n=485 academic, n=129 FTR) attended all ACTivator workshops across 2021, with a further 244 (n=162 academic, n=63 research) during 2022 - due to staff long-term sickness and a review of this programme less sessions ran in 2022. | We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS 2023.
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | Following ECI3: Our Leadership and Development Foundation (LDF) provide resilience training and time management training, as well as coaching. Research managers will be expected to attend and complete this training, and protect time for the researchers whom they manage to attend. | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of research managers who engage with LDF activities but will collect this data going forwards (see action PCDI6). As a minimum we expect 35% of fixed-term staff to engage in these activities, increasing to 50% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Departments, Faculty ADRs to promote these activities to research managers. LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. | The data is regularly collected and reviewed. The pandemic changed the way our staff accessed training and we are therefore also reviewing our delivery modes. From all respondents of CEDARS, 93% completed 1-10 training/CPD activities. Negligible attendance from research staff on LDF/OD sessions related to resilience, but this new addition to the programme will be promoted in 2023. | Data collection of attendees now asks at registration for colleagues to declare their role, which will enable ore thorough acquisition of this data. The LJMU People strategy also promotes this and will provide additional support moving forward.
|  | Following ECI3: Our ACTivator programme provides an 'Attending to You' programme of workshops looking at thinking styles, purpose, confidence, imposter syndrome etc which support the mental wellbeing of academics. Research managers will be expected to discuss these during research appraisals and protect time for researchers to attend, should they wish. | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of research managers who engage with LDF activities but will collect this data going forwards (see action PCDI6). As a minimum we expect 35% of fixed-term staff to engage in these activities, increasing to 50% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Departments, Faculty ADRs and Research managers to promote these activities to research managers. LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. | Data is available through the LJMU LearnUpon portal, reports can be filtered via staff group and role to analyse completion rates. Six workshops themed under the "Attending to You" banner attracted 150 participants across 2021/22, n=33 of which were FTRs which equates to approximately 27% of FTRs. Almost all respondents to our ACTivator evaluation survey (n=25, 96.2%) thought that their participation in the ACTivator workshops was a good use of their time. Of the 134 workshops attended by the 26 individuals, 159 benefits were reported (this included individuals attending multiple workshops and reported multiple impacts across the workshops). This ranged from 1-23 impacts (mean impacts n=6). Awareness of funding opportunities (n=15) was the most reported impact, followed by level of confidence (n=11) and knowledge or collection of research impact (n=10). | As part of the forward facing action plan, we plan to resource more direct support and action for the managers of researchers rather than just support for the researchers themselves. We will also ask colleagues, upon registration, whether they are a PI/RM.
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | LJMU have been actively pursuing this action, specifically through the Bronze Institutional Athena Swan Equality Charter award, and our work towards Silver, which requires the institution to develop, implement and monitor inclusive, equitable and transparent policies and practices. Flexible working requests and actions to support Research Managers to consider these requests form part of this process. In order to further develop this we will pursue Athena Swan accreditation for all University schools/departments (as detailed in ECI1). | We will collect data specific to our RDC cohort and use this as a benchmark in 2021, to improve performance in 2022. | Review the views of all staff, in terms of feasibility, on an annual basis via Athena Swan reporting processes (collect views annually from Dec 2021). Implement CEDARS Spring 2021; re-run Spring 2022. | Head of EDI, Heads of Schools/ Department Faculty ADRs and Research managers to promote Athena Swan goals. Athena Swan Working Group responsible for coordinating this. RDC Lead responsible for implementing CEDARS | All staff have the right to request flexible working regardless of role and it forms part of the benefit information we include in JD/PS at advert stage. We don’t collect data pertaining to the RDC population at present, and a limitation is local manager – staff arrangement which are not recorded with HR. HR have put forward a case with IT to start collating this data and we are hoping this system to be in place in 12 months’ time. HR will be able to report on such data thereafter. This is reflected in forward facing actions. | Moving forwards we aim to utilise the communication platform provided by the RSA to directly link our FTRs to the LJMU Policy Centre and sign post to other mechanisms of support. More focussed data collection should hopefully be enabled by a new data collection mechanism.
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | At school/departmental level, research managers are expected to engage with (and/or lead) research leader meetings, aimed to enable research leaders to contribute to relevant policy and strategy discussions, influencing at research institute and institutional level. Meetings will be held quarterly and minutes will be provided to the management team within the relevant school/department, which will in turn be reported to FMT. | 70% of Schools/Departments to report holding Research Leader meetings, to be captured in the FMT meeting minutes. We will also explore staff experiences/ outcomes of this via CEDARS, but we would not expect this to be captured in the Spring 2021 round. | By Spring 2022, each School/ Department will hold quarterly Research Leader meetings; information to be reported to FMT, and reported to Research and Knowledge Exchange Committee by Associate Deans for Research (ADRs). Implement CEDARS Spring 2021; re-run 2022. | ADRs to support each Faculty to implement. RDC Lead to support with monitoring progress. | We have broken down this progress update, by Faculty- information for which was sought directly from School directors. (i) Arts, Professional and Social Studies- . (ii) Health - ADR leads the only research centre in NAP (LCCS). Regular meetings with individual teams throughout 2021-22 but more recently have organised fortnightly centre meetings to discuss applications and collaborations. The centre reports through the IHR which meets regularly and via NAP SMT. ADR also manages all the research active staff in NAP and meet on a monthly basis to discus their ideas and support needed. (iii) Faculty of Engineering & Technology - ARI has had its own regular meetings. Other groups within FET may not have regular formal meetings but individual groups do have informal meetings regularly (e.g. LOOM and DSRC). (iv) Faculty of Business & Law - Regular research group meetings throughout the Faculty, but activity varies in terms of frequency A template has recently been created for quarterly meetings. (v) Faculty of Science - Regular meetings at Institute and group level reported across all Schools in the Faculty of Science. Research Centres and Institutes (official university structures subject to biennial reviews) meet regularly and at least quarterly and I cite the example of RISES, but research groups in RISES and in the other Schools are ‘unofficial’ structures so they meet informally. | Deprioritised moving forward as this is focussed on all staff with research responsibilities and not focussed on FTRs.
|  | Research managers will support and encourage fixed-term researchers to become actively involved in the Research Staff Association (developed as part of objective ECI6). | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Awareness of these opportunities, feasibility of allowing researchers to take part in this and the outcomes of engagement will be measured via anonymous annual evaluation (online survey). | Review annually, Dec 2021. Implement CEDARS Spring 2021, re-run 2022. | RDC Lead responsible for developing the Researcher Association and implementing monitoring to measure success. Research managers to support their staff to attend, if they wish. | LJMU's organisation development manager and the RDC interim lead have held meetings with local institutions who have successfully set up and coordinate research staff associations. The development of this is currently underway, with support from these two key stakeholders. A proposal has been reviewed and approved by URKEC and all FTRs will be automatically added to the RSA in January 2023. A call for chairs and co-chairs will be released simultaneously, with the aspiration of a co-chair per Faculty that can also provide FTR representation at strategic research meetings. | This action has been prioritised moving forwards and will act as a primary mechanism for engaging with the target group. LDF's organisational development manager has therefore joined the CSG.
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | Researchers must complete all mandatory training on an annual basis. All staff are made aware of this when starting with LJMU and the completion of these courses must be confirmed during appraisals. | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of fixed-term research staff who engage with mandatory training but will collect this data going forwards (see action PCDI6). As a minimum we expect 70% of fixed-term staff to engage in mandatory training, increasing to 85% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | LDF responsible for implementing training and collecting monitoring data. RDC lead responsible for implementing CEDARS. | Research staff are instructed in the mandatory modules alongside all other staff groups, this data can be reported on. Across the four mandatory modules on the Bribery Act, Diversity, the Prevent Act, and Slavery, FTRs are respectively compliant at 72%, 74%, 58% and 79%, whilst Research Staff (including KTPs) are at 75%, 76%, 65% and 82% compliant. General Academic staff are at 79%, 80%, 86% and 90%, respectively. | Although these targets have been met we will continue to prioritise this activity moving forwards.
|  | Following ECI2 and ECM1: Researchers must engage with the interactive training package that is in the process of being developed that addresses Equality, Diversity and Inclusion. | Pre and post training data will be collected (led by the EDI Manager) to identify immediate changes in knowledge, attitudes and perceptions. Longer-term outcomes will also be captured (all via online surveys). We have no baseline for changes in knowledge, attitudes and perceptions but aim for 50% of research managers and researchers to engage in the training in Year 1 (by September 2022). | Training to be implemented by September 2021. First assessment of engagement /update and changes in attitudes to be measured September 2022. | EDI Manager, LJMU | Research staff are instructed in the mandatory modules alongside all other staff groups, this data can be reported on for Diversity in the workplace. FTRs are respectively compliant at 74%, whilst Research Staff (including KTPs) are at 76% compliant. General Academic staff are at 80%. CEDARs data indicate that 15% of all respondents participated in EDI training, as did 26% RS. A further 10% all respondents and 15% RS expressed a desire to complete this in the future. | These success measures have been achieved, but this action will continue to be prioritised for both FTRs and RMs.
|  | Following ECM4: Researchers will be encouraged to join the Researcher Association. | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Awareness of these opportunities, feasibility of allowing researchers to take part in this and the outcomes of engagement will be measured via anonymous annual evaluation (online survey). | Review annually, Dec 2021. Implement CEDARS Spring 2021. | Research managers and fixed-term researchers to advocate. RDC Lead to set up the group and monitor progress. | LJMU's organisation development manager and the RDC interim lead have held meetings with local institutions who have successfully set up and coordinate research staff associations. The development of this is currently underway, with support from these two key stakeholders. A proposal has been reviewed and approved by URKEC and all FTRs will be automatically added to the RSA in January 2023. A call for chairs and co-chairs will be released simultaneously, with the aspiration of a co-chair per Faculty that can also provide FTR representation at strategic research meetings. | This action has been prioritised moving forwards and will act as a primary mechanism for engaging with the target group. LDF's organisational development manager has therefore joined the CSG.
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | Researchers must read the Faculty research handbook [ECI1] and complete all mandatory modules. | 100% of research staff must complete the mandatory modules. Staff awareness and experiences will continue to be monitored using CEDARS and the results using to continually inform activities. | Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Department Faculty ADRs and Research managers to promote. RDC lead responsible for ensuring CEDARS is implemented. | Research staff are instructed in the mandatory modules alongside all other staff groups, this data can be reported on. The completion rates for mandatory training for FTRs as at 20th Jan 2023 were: Bribery Act 72%; Diversity in the Workplace 74%; Prevent 58% and Modern Slavery 79%. CEDARS data: 52% overall and 64% of research staff said they were familiar with LJMU mechanisms to report incidents of research misconduct. 49% (73% of research staff) said that they have undertaken equality, diversity and inclusion training. 60% (68% of research staff) agreed that they were familiar with LJMU's mechanisms to report incidents of discrimination. | Three of the four mandatory modules have been completed by FTRs to the rate stated in our success measure. That said, we will continue to build on this moving forwards, as reflected in our forward facing action plan. Further, evaluation will be built in to understand the perceived value of these.
|  | Following ECI5: All researchers must engage with the Research Integrity activities that are being developed. This includes ensuring awareness and understanding of the Preventing Harm in Research resource and actions to address Poor Practice. | Researchers to engage with training activities regarding Integrity which will be incorporated into our researcher development activities by the LDF (e.g. ACTivator). There is no baseline to measure success but we would expect 35% of researchers to attend/engage with Integrity Training during Year 1 (aligned with other action plan targets). We do not collect specific data on the numbers of research managers who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Research Integrity to be incorporated into our researcher development activities by the LDF by September 2021. Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | The LDF to incorporate Research Integrity into researcher development activities, and collect satisfaction and outcomes data annually. Research Managers to promote this to staff. CEDARS to be implemented by RDC lead. | Attendance and completion records are available via the Libcal development system, and evaluation data is collected. From our attendance records, a total of 686 staff (n=485 academic, n=129 FTR) attended all ACTivator workshops across 2021, with a further 244 (n=162 academic, n=63 research) during 2022 - due to staff long-term sickness and a review of this programme less sessions ran in 2022. Almost all respondents to our ACTivator evaluation survey (n=25, 96.2%) thought that their participation in the ACTivator workshops was a good use of their time. Of the 134 workshops attended by the 26 individuals, 159 benefits were reported (this included individuals attending multiple workshops and reported multiple impacts across the workshops). This ranged from 1-23 impacts (mean impacts n=6). Awareness of funding opportunities (n=15) was the most reported impact, followed by level of confidence (n=11) and knowledge or collection of research impact (n=10). | We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS 2023.
ECR3 | Take positive action towards maintaining their wellbeing and mental health | Following ECI3: Researchers will be encouraged to make use of the staff mental health/wellbeing support available and report to their line manager any issues relating to workload at the earliest opportunity, rather than wait for their appraisal. | Numbers of fixed-term research staff attending these activities will be measured. There is no baseline to measure success but we expect 90% of staff will report feeling confident to report issues to line managers and to make use of LJMU support services. This will be measured via CEDARS. | Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Department LDF and Research managers to promote and support mental wellbeing. CEDARS to be implemented by RDC lead. | CEDARs data: For those managing researchers, 83% felt confident to respond to any issues relating to health and wellbeing. 40% of all CEDARS respondents (and 36.4% of research staff) would like to undertake training on mental health and wellbeing. 37% (and 50% of research staff) felt that their working environment supported their mental health and wellbeing, 72% (82% research staff) said they take positive action to maintain mental health and wellbeing. | These data are promising, will act as a benchmark and have informed actions included in our 2023-25 plan relating to mental wellbeing.
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | LJMU have specific mechanisms in place to ensure researchers (all staff) can report any harassment, bullying, research misconduct or discriminatory behaviour. In line with ECI5, this will be better promoted to researchers. Researchers will be expected to attend ACTivator workshops that include sessions on research integrity (to be developed as part of action ECI5). | We have no baseline on which to measure change, but we expect that 75% of researchers will report that they are aware of the mechanisms by which they can report any harassment, bullying, research misconduct or discriminatory behaviour (in Spring 2021). We want to build on this to achieve 85% awareness by Spring 2022. This evidence will be collected via CEDARS. | Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Department LDF and Research managers to promote and support mental wellbeing. CEDARS to be implemented by RDC lead. | Policies for harassment and bullying are applicable for all staff. CEDARS data: 64 of all respondents (and 68% of research staff) agreed that they were familiar with LJMU's mechanisms to report bullying and harassment. 52% (64% of research staff) said they were familiar with LJMU mechanisms to report incidents of research misconduct. | These CEDARS data provide a useful benchmark for action in LJMU;'s forward facing action plan.
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | In line with objective ECI6, researchers will be encouraged to attend the Researcher Association. This will provide the mechanism for staff to actively contribute to discussions relating to policies and processes. | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Awareness of these opportunities, feasibility of allowing researchers to take part in this and the outcomes of engagement will be measured via anonymous annual evaluation (online survey). | Review annually, Dec 2021. Implement CEDARS Spring 2021. | Research managers and fixed-term researchers to advocate. RDC Lead to set up the group and monitor progress. | LJMU's organisation development manager and the RDC interim lead have held meetings with local institutions who have successfully set up and coordinate research staff associations. The development of this is currently underway, with support from these two key stakeholders. A proposal has been reviewed and approved by URKEC and all FTRs will be automatically added to the RSA in January 2023. A call for chairs and co-chairs will be released simultaneously, with the aspiration of a co-chair per Faculty that can also provide FTR representation at strategic research meetings. | This action has been prioritised moving forwards and will act as a primary mechanism for engaging with the target group. LDF's organisational development manager has therefore joined the CSG.
|  | Researchers are provided with the opportunity to take part in University-wide initiatives, including this Concordat Steering Group and Athena Swan, for example. | Concordat cohort engagement with these activities will be measured through Committee membership. We would expect at least one fixed-term research staff member to be represented across key University-wide initiatives. Staff will report opportunities to engage with initiatives within the CEDARS (alongside their experiences and outcomes of this engagement). We have no baseline, but would expect 60% of staff to report awareness of opportunities to engage within the Spring 2021 CEDARS survey. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | Research managers and fixed-term researchers to advocate. RDC Lead to set up the group and monitor progress. | CEDARS free text data reveal that some colleagues feel the pandemic enabled ore time for training opportunities/or opportunity to take part in University wide initiatives and others felt their time was more pressured. | FTR representation on CSG has undulated during the last 2y phase of CAP delivery. This is due to the nature of short contracts. Currently, we have one representative but this has varied from as high as n=6. formation of the RSA should provide ore direct communication and engagement with the target group, and ensure membership on key research committees.
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | Action links with ECI4: LJMU holds the Bronze Athena Swan award which requires the institution to develop, implement and monitor open, transparent and merit-based recruitment. We are working towards our Silver award and will pursue accreditation for all University schools/departments. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). | Deadline for submissions April 2021, April 2022 | LJMU’s Athena SWAN Working Group | The School of Pharmacy and Biomedical Sciences was Awarded an Athena SWAN Bronze Award in 2021, and the final department in the Faculty of Science (School of Biological and Environmental Sciences) was awarded Bronze status earlier in 2022. Other Schools; LJMU Business School and the Astrophysics Research Institute have also been successful in securing Bronze awards. The School of Sport and Exercise Sciences is now preparing for a Silver submission and LJMU is preparing to submit a Silver Institutional Award. LJMU was awarded a Race Equality Charter Bronze Award in 2022 and, at the time, was one of only 24 Universities to hold the Award. | All Faculty of Sciences School snow have Athena SWAN Bronze awards, as well as the LJMU Business School and the Astrophysics Research Institute
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | Builds on action ECI1: All staff should receive a Staff Induction which includes receiving an induction handbook that provides details about the RDC. | Previous: We had previously measured the number of staff engaging with Inductions on a 3-yearly basis. Our data for all academic staff suggests that 62.5% of staff have had an Induction. Data specific to staff on fixed-term contracts is not collected, although this will be addressed as part of our action plan (e.g. through actions ECI1 and ECI5) and we have a target that 70% of fixed-term research staff will receive an induction by the end of 2021, rising to 85% by December 2022. | HR to monitor the numbers of Inductions taking place. | HR responsible for implementation and monitoring. | LJMU have a standardised approach to induction that applies centrally and at local level Inductions. However, data is not captured currently specific to FTRs, and this action will be carried forward. | Carried forward.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | Links to action ECI1: As part of the development of the Faculty Brochures, we will include information about the institutional and local research strategy, the individual’s role within that strategy, support and career development opportunities including appraisal. Handbooks will advocate for engagement with CEDARS and set out the University’s commitment to the Principles of the Concordat to Support the Career Development of Researchers. | Completion rate for CEDARS to exceed the sector benchmark for CROS (24% in 2017) by achieving 35% completion amongst fixed-term contract researchers. | Handbooks to be updated by April 2021. Implement CEDARS Spring 2021; run again in Spring 2022. | HR responsible for implementation; RDC lead responsible for ensuring CEDARS is implemented. | HESA Staff Record data (October 2022) show LJMU currently employs n=128 Research-only staff. 22 R-only staff completed CEDARS = 17%. | We achieved far below our aspiration of exceeding benchmark response rate. This is potentially due to the timing of the CEDARS launch, summer 2022. During this time many colleagues take annual leave and/or have the increased burden of childcare and caring responsibilities during summer holidays. We will carry forward to revise our timing and communications strategy.
|  | Links to action ECI4: LJMU holds the Bronze Institutional Athena Swan Equality Charter award which requires the institution to deliver on an action plan that includes the development, implementation and monitoring of open, transparent and merit-based recruitment. We are working towards our Silver award and will pursue accreditation for all University schools/departments. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). | Deadline for submissions April 2021, April 2022 | LJMU’s Athena SWAN Working Group | The School of Pharmacy and Biomedical Sciences was Awarded an Athena SWAN Bronze Award in 2021, and the final department in the Faculty of Science (School of Biological and Environmental Sciences) was awarded Bronze status earlier in 2022. Other Schools; LJMU Business School and the Astrophysics Research Institute have also been successful in securing Bronze awards. The School of Sport and Exercise Sciences is now preparing for a Silver submission and LJMU is preparing to submit a Silver Institutional Award. LJMU was awarded a Race Equality Charter Bronze Award in 2022 and, at the time, was one of only 24 Universities to hold the Award. | All Faculty of Sciences Schools now have Athena SWAN Bronze awards, as well as the LJMU Business School and the Astrophysics Research Institute
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | LJMU offer specific training for line managers and project managers through LDF and the ACTivator programme, however the issue of fixed-term researchers (and others) not having research-experienced line management is a big issue in many parts of the University. As well as ensuring all line managers complete the mandatory modules, we will prioritise fixed-term researchers for mentorship, so they have an experienced mentor in addition to their line manager to support their career development, progression and wellbeing. | Our data show that we have an extensive mentorship programme in place, however we do not collect data specifically regarding externally funded fixed-term researchers. We therefore have no benchmark for success, but expect that a minimum of 10 fixed-term researchers have a dedicated mentor to focus on career development, progression and wellbeing. We would want this to raise to 20 by Spring 2022. | Implement CEDARS Spring 2021; run again in Spring 2022. | LDF are responsible for implementing, promoting and monitoring uptake of training; RDC Lead is responsible for implementing CEDARS. | This data is currently not collected and the action will be carried forward. Surveys and focus groups reveal that a large number of casual/non-recorded mentoring occurs in the institution. | This action has been carried forward.
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | Links to action ECI4: LJMU holds the Bronze Institutional Athena Swan Equality Charter award which requires the institution to deliver on an action plan that includes the development, implementation and monitoring of open, transparent and merit-based recruitment. We are working towards our Silver award and will pursue accreditation for all University schools/departments. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). | Deadline for submissions April 2021, April 2022 | LJMU’s Athena SWAN Working Group | The School of Pharmacy and Biomedical Sciences was Awarded an Athena SWAN Bronze Award in 2021, and the final department in the Faculty of Science (School of Biological and Environmental Sciences) was awarded Bronze status earlier in 2022. Other Schools; LJMU Business School and the Astrophysics Research Institute have also been successful in securing Bronze awards. The School of Sport and Exercise Sciences is now preparing for a Silver submission and LJMU is preparing to submit a Silver Institutional Award. LJMU was awarded a Race Equality Charter Bronze Award in 2022 and, at the time, was one of only 24 Universities to hold the Award. | All Faculty of Sciences Schools now have Athena SWAN Bronze awards, as well as the LJMU Business School and the Astrophysics Research Institute
|  | Equal opportunities data will be collected about promotion and specific actions taken to increase awareness of this route amongst research managers and fixed-term researchers. | Staff satisfaction with people management will be measured through CEDARS. 70% of fixed-term researchers will demonstrate satisfaction when CEDARS runs in 2022. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | HR | 22% of RS respondents felt that their immediate line manager is supportive towards promotion, and only 5% expressed that promotions were made on merit. Whereas this reached 50% in all respondents, but only 30% felt that promotions were made on merit. Importantly, the promotion pathway was not clear to >20% RS and >40% of all respondents, which supports a clear forward facing action to attempt to rectify. | A large number of respondents did not respond to these questions which may have skewed the data. A forward facing action is to revise timing of CEDARS and communications strategy to enable more valid data collection. We will also seek to remove confusion regarding the promotion process.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | A review (baseline) of staff on fixed-term contracts is currently underway and will be completed during the implementation of this current action plan. The review is exploring the numbers of staff of fixed-term contracts, and characteristics including numbers of fixed-term staff, retention and redeployment figures. | The results and implications of the review will be completed during 2021 and the findings reported by the RDC Lead to LJMU's Executive Leadership Team and used to inform specific actions which we anticipate to include methods to reduce reliance on short-term rolling contracts. | Actions to be formed and implemented by Dec 2021. | Head of Contracts, HR leading the review. | This action will be carried forward; this constitutes one action that has been rescheduled due to shift in colleague workloads following the pandemic and those challenges outlined in the executive report. | This action will be carried forward.
|  | We will use the information from the review to develop actions to reduce reliance on short-term fixed-term contracts. The Concordat, EDI and Race Charter will provide our catalysts for change. This will provide the opportunity to gain a cross-University view of available resource. | Success will include improved levels of mental wellbeing and productivity as measured by HR data (retention, sickness) and through CEDARS; we will collect a baseline for this amongst the RDC cohort via CEDARS in Spring 2021 and aim to a 10-20% improvement on this by the 2022 survey. | Implement CEDARS Spring 2021; re-run 2022. | Head of Contracts, HR, RDC Lead to implement and monitor this action. | In 2021 and 2022, approximately 20% of FTRs reported sickness absence related to a mental health condition, which is broadly in line with the whole university figures. Voluntary FTR turnover has decreased from 17.2% in 2020 to 9.6% in 2021 and 9.9% in 2022.30% of all respondents and 25% FTRs completed training in mental health and wellbeing (CEDARS). Free text responses indicated that the pandemic adversely affected mental health and wellbeing in staff with research responsibilities and FTRs. | In response to these data, from FTRs and wider staff, LJMU have resourced increased support for colleague mental health and wellbeing (as described in forward facing action plan). Forward actions centre around raising awareness of these primarily through the RSA.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | Following ECI6: We will develop a Researcher Association, led on a voluntary basis by researchers, with the aim of contributing to Institutional policy and practice development and developing best practice. The Association will feed in to the Concordat Steering Group, which reports directly to the URKEC. | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Staff will report active engagement in this group; engagement with Institutional policy and practice development will be collected by the RDC lead and measured via anonymous annual evaluation (online survey). | By Sep 2021 | RDC Lead. | LJMU's organisation development manager and the RDC interim lead have held meetings with local institutions who have successfully set up and coordinate research staff associations. The development of this is currently underway, with support from these two key stakeholders. A proposal has been reviewed and approved by URKEC and all FTRs will be automatically added to the RSA in January 2023. A call for chairs and co-chairs will be released simultaneously, with the aspiration of a co-chair per Faculty that can also provide FTR representation at strategic research meetings. | This action has been prioritised moving forwards and will act as a primary mechanism for engaging with the target group. LDF's organisational development manager has therefore joined the CSG.
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | Researcher managers must complete all mandatory LJMU training modules. We will explore optimal ways to identify research managers so that we can monitor these activities. At present, our LJMU HR systems are quite devolved so we need to engage with HR at Institutional level to enable us to monitor this. Research managers will also be encouraged through RDC promotional activities (e.g. ECI1) to participate in wider ACTivator and LDF training. | 100% of research staff must complete the mandatory modules. Staff awareness and experiences will continue to be monitored using CEDARS and the results using to continually inform activities. | Implement CEDARS Spring 2021; re-run 2022. | Heads of Schools/ Department Faculty ADRs and Research managers to promote. RDC lead responsible for ensuring CEDARS is implemented. | The completion rates for mandatory training for FTC Researchers as at 20th Jan 2023 were: Bribery Act 72%; Diversity in the Workplace 74%; Prevent 58% and Modern Slavery 79%. Research managers are instructed in the mandatory modules alongside all other staff groups, this data can be reported on. CEDARS data: 60% overall and 64% of FTRs said they were familiar with LJMU mechanisms to report incidents of research misconduct. 49% (73% of research staff) said that they have undertaken equality, diversity and inclusion training. 60% (68% of research staff) agreed that they were familiar with LJMU's mechanisms to report incidents of discrimination. | Three of the four mandatory modules have been completed by FTRs to the rate stated in our success measure. That said, we will continue to build on this moving forwards, as reflected in our forward facing action plan. Further, evaluation will be built in to understand the perceived value of these. All comms primarily via RSA.
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and Codes of Practice, institutional policies, and the terms and conditions of grant funding | In line with ECI1, research managers must familiarise themselves with the Faculty Brochure and materials that provide details about our Codes of Practice. | We have no baseline on which to measure success but we would expect 70% of research managers to demonstrate awareness of the RDC, to be measured via the CEDARS survey. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | Research managers responsible for engaging with materials; HR responsible for implementation; RDC lead responsible for ensuring CEDARS is implemented. | From all respondent to CEDARS, 22% expressed some understanding of the RDC, and a further 30% were aware of it but did not understand all of the detail. Slightly less, (16% and 28%, respectively) expressed understanding and awareness of the concordat to support research integrity. Of RS, 36% had some understanding of the RDS and 23% were aware of it but did not fully understand the detail. Of these, 23% and 18% (respectively) expressed understanding ad awareness of the concordat to support research integrity. | These figures will act as a benchmark for future improvement.
|  | Following ECI5: The University has processes in place to incorporate Research Integrity into all of the researcher development (e.g. ACTivator) workshops as a common thread that runs throughout; the content will be shaped by the fixed-term researchers (via the Researcher Association (see ECI6). | Research Integrity to be incorporated into our researcher development activities by the LDF (e.g. ACTivator). There is no baseline to measure success but we would expect 35% of the Concordat cohort to attend during Year 1 (aligned with other action plan targets). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Research Integrity to be incorporated into our researcher development activities by the LDF by September 2021. Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | Research managers responsible for engaging with training. The LDF to incorporate Research Integrity into researcher development activities, and collect satisfaction and outcomes data annually. CEDARS to be implemented by RDC lead. | The data is regularly collected and reviewed. The pandemic changed the way our staff accessed training and we are therefore also reviewing our delivery modes. Since lockdown rules have been relaxed, the ACTivator workshops have been delivered as a mixture of in-person and online, with the ACTivator evaluation revealing qualitative data that those attending felt that there were advantages to both forms of delivery and a mixed approach is felt appropriate to continue. | The review of these developmental activities remains ongoing and will be launched later in 2023.
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | Research managers must engage will all LJMU EDI training, including that is outlined within objective EI5. This training covers specific modules on recruitment, promotion and rewards. This also includes aspects specific to Athena Swan and the Race Charter highlighted across this action plan (e.g. EI6). | Progress against this will be measured through a range of actions related to this e.g. ECI5 (Athena Swan). Staff satisfaction with people management will be measured through CEDARS. 70% of fixed-term researchers will demonstrate satisfaction when CEDARS runs in 2022. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | HR and EDI are responsible for implementing actions related to the Race Charter. The RDC Lead will implement monitoring processes. | 22% of RS respondents felt that their immediate line manager is supportive towards promotion, and only 5% expressed that promotions were made on merit. Whereas this reached 50% in all respondents, but only 30% felt that promotions were made on merit. Importantly, the promotion pathway was not clear to >20% RS and >40% of all respondents, which supports a clear forward facing action to attempt to rectify. | A large number of respondents did not respond to these questions which may have skewed the data. A forward facing action is to revise timing of CEDARS and communications strategy to enable more valid data collection. We will also seek to remove confusion regarding the promotion process.
|  | The Vitae Researcher Development Framework (RDF) offers structure for research managers to use during appraisals (although is not appropriate for all subjects). The use of this framework will be advocated to research managers during line management training and promoted by LDF. | Use (and associated expected/actual) outcomes of the Vitae RDF will be explored via Appraisals. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | LDF, research managers | This action will be carried forward. | This action will be carried forward.
|  | Promotion of fixed-term research staff through Readership and Professorship will be tracked. This data is not currently collected for fixed-term research staff. | We will collect data specific to our RDC cohort and use this as a benchmark in 2021, to improve performance in 2022. We will explore staff awareness of opportunities to apply for this route via CEDARS and attendance at progression events (e.g. 110 academic staff attended our most recent progression event; specific data will be collected related to the Concordat cohort). | Review annually Dec 20201 and Dec 2022. | HR to collate data, RDC Lead to implement monitoring data. | In the 3 year period 2020-22 no FTRs applied for promotion to either Reader or Professor. | Forward facing actions specific to promotion focus on raising awareness and education FTRs about these pathways. The establishment of a RSA will revolutionise the work of the CSG in this area and also aim to feedback to research forums for RMs to improve practice.
|  | Relates to Action ECI5: LJMU hold the Institutional Bronze Athena Swan award which requires the institution to deliver an action plan to develop, implement and monitor inclusive, equitable and transparent policies and practices. We will pursue accreditation for all University schools/departments. | STEMM departments to submit: April 2021 - Astrophysics Research Institute, Pharmacy & Biomolecular Sciences; by April 2022 - Humanities & Social Science, Nursing and Allied Health, Public Health Institute (resubmission), Built Environment (resubmission). | Deadline for submissions April 2021, April 2022 | LJMU’s Athena SWAN Working Group | The School of Pharmacy and Biomedical Sciences was Awarded an Athena SWAN Bronze Award in 2021, and the final department in the Faculty of Science (School of Biological and Environmental Sciences) was awarded Bronze status earlier in 2022. Other Schools; LJMU Business School and the Astrophysics Research Institute have also been successful in securing Bronze awards. The School of Sport and Exercise Sciences is now preparing for a Silver submission and LJMU is preparing to submit a Silver Institutional Award. LJMU was awarded a Race Equality Charter Bronze Award in 2022 and, at the time, was one of only 24 Universities to hold the Award. | All Faculty of Sciences Schools now have Athena SWAN Bronze awards, as well as the LJMU Business School and the Astrophysics Research Institute
EM4 | Actively engage in regular constructive performance management with their researchers | Research managers should hold regular 1-1 meetings with researchers to discuss issues relating to wellbeing, workload and performance. This is more formally monitored through the PDPR. | 100% of staff should have a PDPR. Staff engagement in 1-1s and the effectiveness and satisfaction of this will be explored within CEDARS. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | HR and research managers to promote and implement appraisals, HR to monitor, RDC Lead to implement CEDARS. | Uploaded completion of appraisals for FTRs was - 11.2% in 2020, 30.2% in 2021 and 13.1% in 2022. 22% of FTR respondents felt that their immediate line manager is supportive towards promotion, and only 5% expressed that promotions were made on merit. Whereas this reached 50% in all respondents, but only 30% felt that promotions were made on merit. Importantly, the promotion pathway was not clear to >20% RS and >40% of all respondents, which supports a clear forward facing action to attempt to rectify. | A large number of respondents did not respond to these questions which may have skewed the data. A forward facing action is to revise timing of CEDARS and communications strategy to enable more valid data collection. We will also seek to remove confusion regarding the promotion process.
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | Following action ECI6: Research managers within schools/departments will be responsible for engaging in quarterly research leader meetings to provide opportunity for research group leaders to contribute to discussions on department, Faculty and Institutional strategy. The minutes of these meetings will be fed into the department Management Team (which will subsequently be fed into FMTs and our Research and Knowledge Exchange Committee). | 70% of Schools/Departments to report holding Research Leaders meetings, to be captured in the FMT meeting minutes. We will also explore staff experiences/ outcomes of this via CEDARS, but we would not expect this to be captured in the Spring 2021 round. | By Spring 2022, each School/ Department will hold quarterly Research Leader meetings; information to be reported to FMT, and reported to Research and Knowledge Exchange Committee by Associate Deans for Research (ADRs). Implement CEDARS Spring 2021; re-run 2022. | ADRs to support each Faculty to implement. RDC Lead to support with monitoring progress. | We have broken down this progress update, by Faculty- information for which was sought directly from School directors. (i) Arts, Professional and Social Studies- . (ii) Health - ADR leads the only research centre in NAP (LCCS). Regular meetings with individual teams throughout 2021-22 but more recently have organised fortnightly centre meetings to discuss applications and collaborations. The centre reports through the IHR which meets regularly and via NAP SMT. ADR also manages all the research active staff in NAP and meet on a monthly basis to discus their ideas and support needed. (iii) Faculty of Engineering & Technology - ARI has had its own regular meetings. Other groups within FET may not have regular formal meetings but individual groups do have informal meetings regularly (e.g. LOOM and DSRC). (iv) Faculty of Business & Law - Regular research group meetings throughout the Faculty, but activity varies in terms of frequency A template has recently been created for quarterly meetings. (v) Faculty of Science - Regular meetings at Institute and group level reported across all Schools in the Faculty of Science. Research Centres and Institutes (official university structures subject to biennial reviews) meet regularly and at least quarterly and I cite the example of RISES, but research groups in RISES and in the other Schools are ‘unofficial’ structures so they meet informally. | Deprioritised moving forward as this is focussed on all staff with research responsibilities and not focussed on FTRs.
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | Following ECI5: All researchers must engage in research integrity training and support that is offered. | There will be no benchmark to measure success but we would expect 50% of the Concordat cohort to attend during Year 1. Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | EDI, Research managers | Attendance and completion records are now collected and available via the Libcal development system. Research integrity has been a topic covered within ACTivator sessions, though not as it's own standalone workshop - this will be examined as part of the ongoing action plan. Of all respondents to CEDARS, 16% were aware and understood the concordat to support research integrity, and 28% were aware but did not understand all detail. In RS, 23% and 18% were reported, respectively. LJMU also have an annual research misconduct report, produced by the head of research excellence, and this has received no reports in the last 2 year cycle. | The research development activity is currently under review and integration of research integrity will be considered.
ER2 | Understand their reporting obligations and responsibilities | This obligation links into the actions which are addressed within Action ECI5 relating to research integrity. | Research Integrity to be incorporated into our researcher development activities by the LDF (e.g. ACTivator). There is no baseline to measure success but we would expect 35% of the Concordat cohort to attend during Year 1 (aligned with other action plan targets). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey. | Research Integrity to be incorporated into our researcher development activities by the LDF by September 2021. Review LDF monitoring data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021; re-run 2022. | The LDF to incorporate Research Integrity into researcher development activities, and collect satisfaction and outcomes data annually. CEDARS to be implemented by RDC lead. | Attendance and completion records are now collected and available via the Libcal development system. n=26 staff completed the survey assessing satisfaction and outcomes- the majority of those who had engaged in the survey being on open-ended (permanent and core-funded) contracts (n=18, 69.2%). Smaller proportions on were on fixed term (n=6, 23.1%) and externally funded contracts (n=1, 3.8%), and one person (3.8%) was unsure of their contract type. 7 interviews semi-structured interviews were conducted with; Research fellow, Reader, Associate director, Research funding coordinator, Senior lecturer, PhD researcher, Professor. From our attendance records, a total of 686 staff (n=485 academic, n=129 FTR) attended all ACTivator workshops across 2021, with a further 244 (n=162 academic, n=63 research) during 2022 - due to staff long-term sickness and a review of this programme less sessions ran in 2022. | We recorded low FTR representation in surveys and interviews, which we will proactively seek moving forward via the RSA.
ER3 | Positively engage with performance management discussions and reviews with their managers | All researchers are expected to participate in 1-1s and appraisals. Further, researchers are expected to engage with the relevant LDF and ACTivator programmes/workshops and consider ways to implement this learning to shape their performance. | 100% of staff should have an appraisal. Staff engagement in 1-1s and the effectiveness and satisfaction of this will be explored within CEDARS with a target that 80% of staff will report feeling that they have opportunities to discuss performance management. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022.. | School Directors and Research managers responsible for ensuring appraisals take place. RDC Lead responsible for monitoring this activity. | Centralised data reveal that 30.2% of FTRs completed an annual appraisal in 2021, and 13.1% in 2022. Compliance amongst all other staff was 59.3% and 35.4%, respectively across years. From CEDARS responses, 88% of all staff competed a PDPR, and 77% RS did. However, in both groups only 50% reported that this was a useful process. Free text responses reveal that the opportunity to discuss performance management is there but workload can not always be adjusted to accommodate research needs. | These data reveal a significant gap between our aspiration and reality and thus constitute a priority for our forward facing action plan. A large number of respondents did not respond to these questions in CEDARS which may have skewed the data. A forward facing action is to revise timing of CEDARS and communications strategy to enable more valid data collection. We will also seek to remove confusion regarding the promotion process.
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | In line with objective ECI6, researchers will be encouraged to attend the Researcher Association. This will provide the mechanism for staff to actively contribute to discussions relating to policies and processes. | By September 2021, the Concordat Steering Group will have developed an active Research Staff Association that is represented by 15 fixed-term researchers across all Faculties. Staff will report active engagement in this group; engagement with Institutional policy and practice development will be collected by the RDC lead and measured via anonymous annual evaluation (online survey). | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022.. | RDC Lead to implement. | LJMU's organisation development manager and the RDC interim lead have held meetings with local institutions who have successfully set up and coordinate research staff associations. The development of this is currently underway, with support from these two key stakeholders. A proposal has been reviewed and approved by URKEC and all FTRs will be automatically added to the RSA in January 2023. A call for chairs and co-chairs will be released simultaneously, with the aspiration of a co-chair per Faculty that can also provide FTR representation at strategic research meetings. | This action has been prioritised moving forwards and will act as a primary mechanism for engaging with the target group. LDF's organisational development manager has therefore joined the CSG.
|  | Researchers are provided with the opportunity to take part in University-wide initiatives, including this Concordat Steering Group and Athena Swan, for example. | 75% of staff on fixed-term contracts will report having opportunity to participate in activities that influence and feed into University-wide initiatives; 35% will report participating in such activities by Dec 2021. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022.. | Research managers to provide support; RDC Lead to monitor and implement CEDARS. | 40% of RS reported a need to develop their research identity and 45% reported that this was supported by their manager. However, free text responses reveal that opportunities to participate in university wide initiatives was hindered by the pandemic. | FTR representation on CSG has undulated during the last 2y phase of CAP delivery. This is due to the nature of short contracts. Currently, we have one representative but this has varied from as high as n=6. formation of the RSA should provide ore direct communication and engagement with the target group, and ensure membership on key research committees. Plan for the SRA also include strategic placement of RS on Faculties research and knowledge exchange committees- ensuring that the target group have a voice in the research infrastructure at LJMU.
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | We will include reference to the Researcher Development Concordat (RDC) within the job description/person specification for fixed-term research posts to state: LJMU are committed to adhering to the Principles set out in the Researcher Development Concordat; in line with this all fixed-term researchers will be supported to complete 10 days professional development activities per year (pro-rata). | Success: we would expect this to be included in all induction materials/contracts by April 2021. 100% of staff to report discussing this in July 2021 appraisals. | Implement by April 2021, and review progress and outcomes Dec 2021 and Dec 2022 via appraisal information. | HR to implement and collect monitoring data. | The statement "LJMU are committed to adhering to the Principles set out in the Researcher Development Concordat; in line with this all fixed-term researchers will be supported to complete 10 days professional development activities per year (pro-rata)" has been added to our template FTR job descriptions/person specs and also the template confirmation of employment letters. This statement is now requested to be included in all relevant job descriptions. A small number of inconsistencies in use of this statement have been identified, therefore a future action will be to incorporate this in a HR systems check to minimise non-inclusion of this statement. 52% of all respondents to CEDARS had either some understanding of the RDC [22%], or knew of it's existence but did not know all detail [30%]. 59% of FTRs who responded to CEDARS had either some understanding of the RDC [36%] or had heard of it but did not now al the detail [23%]. | This statement has been implemented by means of recommendations, a formal HR check will be considered in a forward facing action plan.
|  | All research managers and researchers will be expected to discuss and plan opportunities for these activities during appraisals and in regular 1-1 meetings. | We have no benchmark, but would expect researchers to engage with a minimum requirement of 5 days by the end of Year 1, building to 8 by the end of Year 2. This information would be collected during appraisals and using the CEDARS survey. | Review progress and outcomes Dec 2021 and Dec 2022 via appraisal information. | School Directors; Research managers to implement and review; RDC Lead to monitor. | n=28 FTRs and n=5 FTRs attended LDF coordinated CPD (Attending to You) in 2021 and 2022, respectively. n=8 (6%) and n=2 FTRs (2%) also attended leadership training across 2021, and 2022, respectively. This equates to 22% and 4%. 10% of all respondents to CEDARS and 5% RS completed leadership training with LDF. 15% of all respondents expressed a desire to complete these, as did 35% RS. However, 95% RS completed 1-10 CPD activates although time was expressed as a significant barrier (55%). Given that 40% RS understood the importance of developing a research identity, this initial pilot data is promising for future roll out of the workshop. | Implementation data has been monitored and revealed that leadership training does not seem to have been prioritised. Narrative around research leadership training should be woven into PDPRs and goal setting for RS.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | LJMU provide an e-learning module for all managers 'Appraisals and Connected Conversations'. We will promote this to managers of fixed-term research staff via School Directors, appraisals and our promotional materials (and to aspiring research managers through the Researcher Association). We will promote this through School Directors and our handbooks (Concordat materials), collect data about the awareness and effectiveness of this via appraisals, CEDARS and through the collection of data specific to our Concordat cohort. | We currently collect data on the numbers of people attending training (with a target to increase this by 10% year-on-year). We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). As a minimum we expect 35% of fixed-term staff to engage in these activities, increasing to 50% in 2022. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | HR, LDF | The Appraisal online session is currently a non-mandatory session, that to date has been completed by 35% of RMs and 34% of fixed term researchers | Moving forward, we intend to make attendance at the appraisal online session mandatory for RMs.
|  | Develop a process that easily identifies those managers of fixed-term research staff so that they can be prompted (by HR) to fulfil their responsibilities here, and provide high quality information and/or sign-posting. This will be used by research leaders, ADRs and other relevant staff to identify research capacity across the University. | By September 2021, we will have a comprehensive overview of managers of fixed-term staff. 75% of research leaders will report knowledge of this, to be reviewed through HR recruitment process and via CEDARS. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | HR | This action constitutes workload that has been shifted due to changes that unfolded as a result of the pandemic and other challenges described in the executive summary. Resultantly, these data is currently not collected and the action will be carried forward. | This action will be carried forward.
|  | A number of staff in our Leadership Development Foundation are qualified coaches and offer 1:1 coaching in conducting and preparing for appraisals. We will offer coaching training to all managers of fixed-term research staff and promote this via School Directors. We will promote this to School Directors, appraisals and our promotional materials (and to aspiring research managers through the Researcher Association). | We do not collect specific data on the numbers of fixed-term research staff who engage with LDF activities but will collect this data going forwards (see action PCDI6). Satisfaction and outcomes will be evaluated with a target of 90% satisfaction (to be collected by LDF) and this information used to develop/refine the courses. Awareness and outcomes of the course will be further measured via the CEDARS survey, with 70% of staff reporting awareness by April 2022. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | HR, LDF | According to our CEDARS data, between 30-50% of all respondents and RS reported either having completed or having a desire to complete various workshops hosted by LDF. The current booking system for training events does not allow attendance data to be divided into different groupings of research role. There is currently a project underway to develop a new booking systems that has a greater integration with the staff record system, which will allow this date to be retrieved. According to our ACTivator evaluation, almost all respondents (n=25, 96.2%) thought that their participation in the ACTivator workshops was a good use of their time. Of the 134 workshops attended by the 26 individuals, 159 benefits were reported (this included individuals attending multiple workshops and reported multiple impacts across the workshops). This ranged from 1-23 impacts (mean impacts n=6). Awareness of funding opportunities (n=15) was the most reported impact, followed by level of confidence (n=11) and knowledge or collection of research impact (n=10). | We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS 2023. There is currently a project underway to develop a new booking systems that has a greater integration with the staff record system, which will allow this date to be retrieved.
|  | The Vitae Wheel offers structure for research managers to use during appraisals. The use of this wheel will be advocated to research managers during line management training and promoted by LDF. | Use (and associated expected/actual) outcomes of the Vitae wheel will be explored via Appraisals. 70% of researchers will report using the wheel, where applicable, via appraisal reviews. This will also be explored via CEDARS. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | LDF, research managers | This action constitutes workload that has been shifted as a result of disruption from the pandemic, and other challenges described in our executive summary. As a result these data are not available but the action will be carried forward and collected via RSA. | This action will be carried forward.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | Our Leadership and Development Foundation (LDF) have a dedicated website that provides information about all training that is offered. In line with objective PCDI6, we will collect information specific to the Concordat Cohort. | We have no benchmark to assess the % of fixed-term contract researchers who engage with LDF training but will start to collect this (see objective PCDI6) and expect to see a 30% increase between Dec 2021 and Dec 2022. | Review annually, Dec 2021 and Dec 2022. | Research managers | Attendance and completion records are now collected and available via the Libcal development system. From our attendance records, a total of 686 staff (n=485 academic, n=129 FTR) attended all ACTivator workshops across 2021, with a further 244 (n=162 academic, n=63 research) during 2022 - due to staff long-term sickness and a review of this programme less sessions ran in 2022. | The current booking system in use records total n of attendees and does not provide information on % of a specific population in LJMU. CRN system is due to be launched in September 2023 and will collect much more comprehensive data regarding % attendees and also protected characteristics, which will only be utilised for reporting group level statistics.
|  | LDF will pilot a 'Being Leadership' series of workshops which will focus on communications, empathy and self-awareness. This will be promoted to fixed-term research staff by promotional materials, School Directors and research managers. | We will collect implementation and outcomes data on the pilot. We will explore attendance, awareness and outcomes via this process and also via CEDARS. | Pilot Feb 2021; implement CEDARS Spring 2021 | LDF | 10% of all respondents to CEDARS and 5% RS completed leadership training with LDF. 15% of all respondents expressed a desire to complete these, as did 35% RS. Given that 40% RS understood the importance of developing a research identity, this initial pilot data is promising for future roll out of the workshop. Implementation of the Leadership programme has been delayed due to the departmental restructure referred to in our executive summary document; a newly developed suite of leadership development support is being designed to launch in September 2023. | Implementation data has been monitored and revealed that leadership training does not seem to have been prioritised. Narrative around research leadership training should be woven into PDPRs and goal setting for RS. A newly developed suite of leadership development support is being designed to launch in September 2023.
|  | Wider development opportunities will be cascaded via our central LJMU communications team and via the Researcher Association. | 75% of staff will recall seeing staff development opportunities via communications (e.g. emails, newsletters) as captured via CEDARS in 2022. | Review annually, Dec 2021. Implement CEDARS Spring 2021; re-run 2022. | LDF and LJMU Communications Team | This action will be carried forwards and communicated directly to the RSA via their mailing list and shared workspace (MS Teams site). | This action has been prioritised moving forwards and will act as a primary mechanism for engaging with the target group. LDF's organisational development manager has therefore joined the CSG.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | Our Leadership and Development Foundation (LDF) and ACTivator workshops provide opportunities for research staff to develop identity and leadership skills. The engagement of fixed-term research staff will be supported via action PCDI1. In line with objective PCDI6, we will collect information specific to the Concordat Cohort. | Success: we would expect fixed-term research staff to engage with a minimum 5 days professional development activity that includes activity to develop research identity and leadership skills. Outcomes will be collected via CEDARS survey and appraisals. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | LDF, research managers | 10% of all respondents to CEDARS and 5% RS completed leadership training with LDF. 15% of all respondents expressed a desire to complete these, as did 35% RS. However, 95% RS completed 1-10 CPD activates although time was expressed as a significant barrier (55%). Given that 40% RS understood the importance of developing a research identity, this initial pilot data is promising for future roll out of the workshop | Implementation data has been monitored and revealed that leadership training does not seem to have been prioritised. Narrative around research leadership training should be woven into PDPRs and goal setting for RS.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | We will commit to exploring the development of an interactive workshop for employers/researchers to liaise with employers to provide job opportunities. We are aware of examples across the sector (e.g. University of Liverpool's Prosper Workshop) and will learn from these to explore the possibility of developing a bespoke workshop for our research community, with a focus on fixed-term researchers. | The development and delivery of a workshop with attendance from at least 40% of staff on fixed-term research contracts. Experiences of this will be captured via pre and post monitoring and engagement with attendees. | April 2022. | Pro-VC Research, LDF | This action constitutes workload that has been shifted as a result of disruption from the pandemic, and other challenges described in our executive summary. As a result these data are not available but the action will be carried forward and collected via RSA. | This action will be carried forward.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | Our ACTivator programme is constantly reviewed and adapted to address emerging needs e.g. the development of the new ‘Being Leadership’ series of workshops has been prompted by feedback from researchers. We will target fixed-term research staff with these activities via the promotional methods described elsewhere (e.g. PCDI1, ECI1) and by implementing data collection measures specific to this cohort. | Attendance by fixed-term research staff at core ACTivator workshops will increase from 16% to 20% (based on overall attendance rates). We will also explore the effectiveness and awareness about these programmes via CEDARS. | Review annually, Dec 2021. Implement CEDARS Spring 2021. | Research managers, fixed-term researchers. | From our attendance records, a total of 686 staff (n=485 academic, n=129 FTR) attended all ACTivator workshops across 2021, with a further 244 (n=162 academic, n=63 research) during 2022 - due to staff long-term sickness and a review of this programme less sessions ran in 2022. From CEDARS data, individual ACTivator sessions were completed or there was a desire t complete by 20-40% respondents. For example, ~15% of all respondents and RS had completed communication and dissemination training, with a further 26=5% expressing interest in completing this session. Almost all respondents (n=25, 96.2%) thought that their participation in the ACTivator workshops was a good use of their time. Of the 134 workshops attended by the 26 individuals, 159 benefits were reported (this included individuals attending multiple workshops and reported multiple impacts across the workshops). This ranged from 1-23 impacts (mean impacts n=6). Awareness of funding opportunities (n=15) was the most reported impact, followed by level of confidence (n=11) and knowledge or collection of research impact (n=10). | The ACTivator series is currently under review in response to the detailed evaluation, analysis performed and resultant recommendations generated. This is in terms of both content and delivery. The new, evolved packages will be launched and communicated in 2023.
|  | ACTivator (and LDF) data is currently collected by gender, Faculty, School and other broad information. We are in the process of adding an indicator to enable us to collect data on contract type. This will enable us to identify progress specific to our Concordat cohort. | Data collection measures will be embedded by April 2021. | 2021-04-01 | Concordat Steering Group Lead to liaise with LDF/HR. | The current booking system for training events does not allow attendance data to be divided into different groupings of research role. There is currently a project underway to develop a new booking systems that has a greater integration with the staff record system, which will allow this date to be retrieved. | There is currently a project underway to develop a new booking systems that has a greater integration with the staff record system, which will allow this date to be retrieved, which constitutes a forward facing action.
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | Managers of fixed-term research staff will be encouraged to discuss this during appraisals. Whilst this (and the LDF/ACTivator programme) are encouraged, this will be actively promoted through the Concordat materials. | 100% of staff should have an appraisal. Fixed-term research staff engagement in these and the effectiveness and satisfaction of this will be explored within CEDARS. | Review annually, Dec 2021 and Dec 2022. | Research Managers | The data for uploaded completion appraisals is 11.% in 2020, 30.2% in 2021 and 13.1% in 2022. From all respondent to CEDARS 88% had an annual appraisal and FTRs reported 77% completion rates. 50% of the FTRs reported finding their appraisal a useful process. Of those who did not participate 60% were recently appointed which may skew this completion data somewhat due to the short terms nature of some research contracts. | Discussions at CSG support an action to make research appraisal mandatory, and will be formally monitored and followed up by HR (forward facing action plan).
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | We will deliver, evaluate and review the ACTivator programme with specific promotion to the managers of fixed-term research staff. This will include data specific to the Concordat cohort (see Action PCD16). We will engage research managers with CEDARS in 2021 to explore implementation and outcome data. | Increased researcher engagement with development activities, specifically core ACTivator workshops with 75% of research managers and fixed-term research staff attending at least one workshop per academic year (there is no current benchmark specifically for this cohort). No benchmark for CEDARS completion but previous CROS survey was 24%; we will aim for 35% completion. | Implement CEDARS Spring 2021 (to run on a two-yearly basis). | LDF, School Directors, Research Managers | From our attendance records, a total of 686 staff (n=485 academic, n=129 FTR) attended all ACTivator workshops across 2021, with a further 244 (n=162 academic, n=63 research) during 2022 - due to staff long-term sickness and a review of this programme less sessions ran in 2022. From CEDARS data, individual ACTivator sessions were completed or there was a desire t complete by 20-40% respondents. For example, ~15% of all respondents and RS had completed communication and dissemination training, with a further 26=5% expressing interest in completing this session. Almost all respondents (n=25, 96.2%) thought that their participation in the ACTivator workshops was a good use of their time. Of the 134 workshops attended by the 26 individuals, 159 benefits were reported (this included individuals attending multiple workshops and reported multiple impacts across the workshops). This ranged from 1-23 impacts (mean impacts n=6). Awareness of funding opportunities (n=15) was the most reported impact, followed by level of confidence (n=11) and knowledge or collection of research impact (n=10). | The ACTivator series is currently under review in response to the detailed evaluation, analysis performed and resultant recommendations generated. This is in terms of both content and delivery. The new, evolved packages will be launched and communicated in 2023.
|  | Fixed-term research staff will be assigned a mentor as part of their Induction process. LDF offer a matching service for existing fixed-term research staff that will be promoted to research managers via School Directors and through Concordat promotion activities (described elsewhere in this action plan). | Success: all new contract research staff will be assigned a mentor. To be measured through the induction process and also via CEDARS. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | HR, LDF, Research Managers | This data is currently not collected and the action will be carried forward. Surveys and focus groups reveal that a large number of casual/non-recorded mentoring occurs in the institution. | This action has been carried forward.
|  | LJMU will are planning to be involved in a pilot led by Salford University for cross-institutional mentoring. Opportunities for fixed-term research staff to engage with this will be promoted via LDF, School Directors and through Concordat promotion activities (described elsewhere in this action plan). | The pilot project will be evaluated and if successful will be rolled out by December 2022. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | LDF | This action was paused due to disruption caused by the pandemic. | This action has been deprioritised in favour of establishing an RSA.
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | Research managers must commit to allowing their staff to engage in the minimum 10 days pro rata and plan this into their resource and project plans accordingly. | We have no benchmark, but would expect researchers to engage with a minimum requirement of 5 days by the end of Year 1, building to 8 by the end of Year 2. This information would be collected during appraisals (line manager monitoring) and using the CEDARS survey. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | School Directors; Research managers | 10% of all respondents to CEDARS and 5% RS completed leadership training with LDF. 15% of all respondents expressed a desire to complete these, as did 35% RS. However, 95% RS completed 1-10 CPD activates although time was expressed as a significant barrier (55%). Given that 40% RS understood the importance of developing a research identity, this initial pilot data is promising for future roll out of the workshop | Implementation data has been monitored and revealed that leadership training does not seem to have been prioritised. Narrative around research leadership training should be woven into PDPRs and goal setting for RS.
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | Research managers will discuss fixed-term research staff development requirements during regular 1-1s and appraisals. Research managers will familiarise themselves with LDF and ACTivator programmes (as a minimum) with specific training requirements (e.g. research skills) identified and acted upon via appraisals. | Increased researcher engagement with development activities, specifically core ACTivator workshops with 75% of research managers and fixed-term research staff attending at least one workshop per academic year (there is no current benchmark specifically for this cohort). | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | School Directors; Research managers | Attendance and completion records are now collected and available via the Libcal development system. Limitations of the current event booking system prevent analysis of specific job roles on programmes, this is being addressed through the new CRM related booking system highlighted above. | There is currently a project underway to develop a new booking systems that has a greater integration with the staff record system, which will allow this date to be retrieved, which constitutes a forward facing action.
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | Ensure the Concordat cohort are engaged with LJMU provision for future research leaders: the Research Team Leadership programme. Deliver, evaluate and review leadership development provision for future research leaders, Engage staff with CEDARS in 2021 and develop an associated action plan. | A minimum of one cohort annually of fixed-term research staff (n=10) to complete the ‘Research Team Leadership programme’. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | School Directors; Research managers | Due to structural changes and other issues (please see references to restructure previously in this document and in executive summary) a tailored Leadership programme has not run yet, with a new suite of leadership programmes being developed for September 2023. n=18 (14%) research specific staff attended general leadership events across 2021/22, with a further n=55 general academic staff across the same period. | The review of researcher development activity is ongoing and will launch in 2023. This will include changes to content, focus, delivery mode and booking system/data monitoring.
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | Fixed-term research staff will familiarise themselves with the professional development opportunities available to them and actively identify how to engage with the minimum 10-days (pro-rata); this should be discussed at appraisals with specific reference to professional and career development goals. | We have no benchmark, but would expect researchers to engage with a minimum requirement of 5 days by the end of Year 1, building to 8 by the end of Year 2. This information would be collected during appraisals (line manager monitoring) and using the CEDARS survey. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | School Directors; Research managers | 10% of all respondents to CEDARS and 5% RS completed leadership training with LDF. 15% of all respondents expressed a desire to complete these, as did 35% RS. However, 95% RS completed 1-10 CPD activates although time was expressed as a significant barrier (55%). Given that 40% RS understood the importance of developing a research identity, this initial pilot data is promising for future roll out of the workshop | Implementation data has been monitored and revealed that leadership training does not seem to have been prioritised. Narrative around research leadership training should be woven into PDPRs and goal setting for RS.
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | Fixed-term research staff will engage with LDF and ACTivator opportunities and actively engage with their mentors. | In line with PCDI6, we will collect data specific to fixed-term research staff to monitor engagement with the LDF and ACTivator provision that is available to staff. We will collect outcomes data through tailored evaluations. We will use CEDARS to collect awareness and impact data. | Review LDF and ACTivator data annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Research managers, fixed-term researchers. | Attendance and completion records are now collected and available via the Libcal development system. From our attendance records, a total of 686 staff (n=485 academic, n=129 FTR) attended all ACTivator workshops across 2021, with a further 244 (n=162 academic, n=63 research) during 2022 - due to staff long-term sickness and a review of this programme less sessions ran in 2022. | The current booking system in use records total n of attendees and does not provide information on % of a specific population in LJMU. CRN system is due to be launched in September 2023 and will collect much more comprehensive data regarding % attendees and also protected characteristics, which will only be utilised for reporting group level statistics.
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | Ensure LJMU Symplectic database is up to date. Consider and develop professional career development plan through appraisals and the use of the Vitae Wheel. | 100% of staff to have an appraisal. 100% of staff will report Symplectic being up to date. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Fixed-term researchers | Appraisal completion data* for FTRs is as follows: 2020 - 11.2%; 2021 - 30.2% and 2022 - 13.1% *these figures are derived from the number of appraisals that were uploaded to the Staff Infobase system | It is currently optional for staff members to upload and store their annual appraisal on the HR system, therefore, we can only report on those who have stored their appraisal, not necessarily on those who have had an appraisal. For the 2023 appraisal cycle, the university has introduced an new performance and review and development system which should allow for more accurate completion data being available.
PCDR4 | Positively engage in career development reviews with their managers | Appraisals provide opportunity to discuss this. All fixed-term research staff to prepare and discuss this meaningfully during appraisals. | 100% of staff to have an appraisal and 60% to cite having meaningful discussions regarding career progressions. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Fixed-term researchers | CEDARS data reveal that 50% of FTRs who participated in an annual appraisal found it a useful and meaningful process and gf these that did not complete it was due to being a relatively new starter. | Discussions at CSG support an action to make research appraisal mandatory, and will be formally monitored and followed up by HR (forward facing action plan).
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | Commit to engaging with LDF and ACTivator programmes to develop research identity and leadership skills. | Awareness and engagement data will be collected by LDF (following implementation of action PCDI6) and will also be measured via CEDARS. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Fixed-term researchers | Of the RS who participated in CEDARS 40% understood the importance of developing research identity and 45% said that this was supported by their research manager. This data is unfortunately skewed as 50% of respondents did not answer either of these questions. | These data can be more meaningful by refining communication strategy surrounding CEDARS and also being ore considerate as to the timing of running CEDARS. The ADR awareness raising events planned for 2023 are an ideal opportunity to communicate this.
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | Continue to run the University’s annual Research & Innovation showcase event with a renewed focus on the following objectives: Grow participation (internal, including contract researchers, and external) Re-design the format and content to facilitate an increased emphasis on learning/development outcomes Involve the Concordat Steering Group in the design, planning and running of the event Establish robust measures to evaluate outcomes and satisfaction | No benchmark for Concordat cohort (fixed-term research staff), but based on previous projections aim to increase participation to 25%. We will also implement robust evaluation to identify the outcomes of engagement for researchers and their managers. | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Fixed-term researchers, URKEC and HR | Attendance data was recorded but that was not disaggregated by role, and action that will be carried forward. It is however worthy of mention that space on the agenda of this annual event has been afforded to raising awareness of the researcher development concordat. In 2021, Dr Hannah Timpson (academic lead) presented a session entitled, Supporting the Career Development of Researchers at LJMU. In 2022, Dr Tori Sprung (Interim academic lead) presented a plenary session entitled, "The Importance of Culture for Researchers to Thrive". | Although progress has been made on this action, we have not implemented robust monitoring or evaluation to identify the outcomes of engagement for researchers and their managers. A future facing action will address this.
|  | Explore the numbers of externally funded research staff applying for Professor and Reader conferment and compare this against the data collected for all applications (and analyse in relation to demographic and other characteristics). | We will continue to monitor our application, shortlisting and award numbers and take remedial action if the proportion of eligible candidates applying for Readership promotion falls below 3% for female staff and 6% for males. We do not have a benchmark for the numbers of Professor and Reader conferment applications by contract type, but will collect this and explore awareness/accessibility of this route by externally funded fixed-term staff (e.g. through staff survey, Spring 2021). | Review annually, Dec 2021 and Dec 2022. Implement CEDARS Spring 2021. | Concordat Steering Group Lead, HR | In the 3 year period 2020-22 no FTRs applied for promotion to either Reader or Professor. | Forward facing actions specific to promotion focus on raising awareness and education FTRs about these pathways. The establishment of a RSA will revolutionise the work of the CSG in this area and also aim to feedback to research forums for RMs to improve practice.
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.