## Template for institutions
| HREiR Action plan template (January 2023-January 2025) | [6 empty] | Add institutional logo
Details
| Institution name: | Liverpool John Moores University |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | 167 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | 27th January 2023 |  |  |  | Research staff |  | 167
| Institutional context: | Researchers employed on externally funded fixed-term contracts [FTRs (n = 126)], based across all Faculties, are the target audience for our new Concordat Action Plan (CAP), although all colleagues with research responsibilities will benefit from the actions described. |  |  |  | Postgraduate researchers |  | 893
[6 empty] | Research and teaching staff |  | 1116
[6 empty] | Teaching-only staff |  | 144 | Academic staff on grade 7 and below listed as Teaching-only staff. This has historically been the case, however, will change slightly with the introduction of the new academic structure. However, for this purpose we’ve opted to use the established reporting approach.
[6 empty] | Technicians |  | 184
[6 empty] | Clinicians |  | 0
[6 empty] | Professional support staff |  | 1260 | Grouped Administration within Professional Services and Faculties into Professional support staff
[6 empty] | Other (please provide numbers and details): |  | Manual support staff - 215 | All of these numbers are headcount
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat. | The statement "LJMU are committed to adhering to the Principles set out in the Researcher Development Concordat; in line with this all fixed-term researchers will be supported to complete 10 days professional development activities per year (pro-rata)" has been developed and is requested to be included in all FTR posts. A centralised HR check will be incorportaed into the job advertisement process. Commitment to concordat also included in new University Strategy2030 and the University RKE plan 2030. | No | June 2023 (HR check) January 2024 (CEDARS) | HR colleagues to implement and CSG to facilitate CEDARS | 100% of FTR job adverts include this text. Increased awareness of colleagues with research management (PI) resonsibilities and fixed term researchers of the RDC to >50% and >70%, respectively.
|  | A consistent (digital) approach to research brochures will be adopted across all faculties, coordinated by ADRs and URKEC. | No | 2024-01-01 | Associate Deans for Research, ProVice Chancellor for Research & Knowledge Exchange, URKEC | All Faculties to develop digital Research Brochures by January 2024 in a standardised format to enhance researcher engagement with this material and in doing so, heighten awareness. Digital 'hits' will be monitored to provide benchmark data on engagement.
|  | Conduct a series of focus groups, per faculty, on research culture and FTRs. Analyse these data and utilise to create an awareness raising workshop, in combination with CEDARS data. ADRs to deliver Faculty sessions, wellbeing team and OD to attend and raise awareness of LJMU centralised support. Additional question in CEDARS to enquire whether i) RMs feel confident to manage a healthy working environemnt that supports mental health and wlellbeing and ii) whether FTRs experience a healthy working environment that supports mental health and wlellbeing. | No | 2023-12-01 | Faculty ADRs to deliver, wellbeing team and OD to support, academic lead of RDC to facilitate and implement CEDARS | >60% of FTRs and wider staff with resaerch responsibilities to express awareness and underesatanding of the reseacher development concordat via CEDARS.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | The RDC principles are now listed within the LJMU Staff Induction Handbook and Induction sessions. We propose further evolving our induction process to include discussion of the RDC principles between FTRs and their PI. This will include a tick checklist, that will need signing by both parties and submitting to HR colleagues. | No | September 2023 (HR check) January 2024 (CEDARS) | HR colleagues; CSG | >80% of returns signed for induction process. Increased awareness of colleagues with research management (PI) resonsibilities and fixed term researchers of the RDC to >50% and >70%, respectively.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Annual data collection of CEDAR in order to accure longitudinal data that can assess change in culture over time, mapped against concordat activity. This measurement of impact will enable the CSG and other key stakeholders to raise awareness of the Concordat and also demonstate impact on research culture and environment. | No | Summer 2023 and Summer 2024 | CSG | Completion of CEDARS, processing, and interpretation of results. Annual report communicated with CSG, URKEC and Research Staff Association (RSA). Aim for 50% completion rates for academic staff and FTRs.
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | The formation of an RSA is currently underway. The RSA will feed into the LJMU Concordat Steering Group (CSG), and members of the RSA will also provide representation of their respective Faculties on Faculty Research and Knowledge Exchange Committee’s, both of which report directly to the University Research and Knowledge Exchange Committee (URKEC). This will give our fixed term research colleagues a voice in strategic meetings that influence LJMU’s research environment and culture. | Yes | 2023-07-01 | Leadership & Development Foundation (OD), CSG and URKEC colleagues | The RSA will be facilitated by Organisational Deelopment (OD) and coordinated, on a voluntary basis, by FTRs themselves. The formaton of the group with Chairs, co-chairs (1 per Faculty) and a co-created terms of reference in place. The set up of an MS Teams site, via whch the RSA will operate, communicate and resoruce share. RSA will formamly submit a report for review and discussion to URKEC, annually.
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | Raise awareness for mental health provision via LJMU staff wellbeing hub. Moving forwards we aim to utilise the communication platform provided by the RSA to directly link our FTRs to the LJMU Policy Centre and sign post to other mechanisms of support. | No | 2023-01-01 | Head of D&I, Staff wellbeing champion, Heads of Department, and Faculty ADRs. RDC academic lead to implement CEDARs | Introduce a question to CEDARS to assess whether FTRs understand how to report and seek support for issues pertaining to mental health and wellbeing. Aspiration is for at least 50% to report that they have knowledge of this.
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | Raise awareness for mental health provision via LJMU staff wellbeing hub | No | 2024-01-01 | Head of D&I, Staff wellbeing champion, Heads of Department, and Faculty ADRs. RDC academic lead to implement CEDARs | Introduce a question to CEDARS to assess whether RMs understand how to report and seek support for issues pertaining to mental health and wellbeing. Aspiration is for at least 50% to report that they have knowledge of this.
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | Raise awareness of the researcher development concordat through targeted Faculty sessions. | No | 2023-12-01 | Faculty ADRs to deliver, wellbeing team and OD to support, academic lead of RDC to facilitate and implement CEDARS | Conduct a series of focus groups, per fcaulty, on research culture and FTRs. Analyse these data and utilise to create an awareness raising workshop, in combination with CEDARS data. ADRs to deliver Faculty sessions, wellbeing team and OD to attend and raise awareness of LJMU centralised support. Additional question in CEDARS to enquire whether i) RMs feel confident to manage a healthy working environemnt that supports mental health and wlellbeing and ii) whether FTRs experience a healthy working environment that supports mental health and wlellbeing.
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | LJMU have been actively pursuing this action, specifically through the Bronze Institutional Athena Swan Equality Charter award, and our work towards Silver, which requires the institution to develop, implement and monitor inclusive, equitable and transparent policies and practices. Flexible working requests and actions to support Research Managers to consider these requests form part of this process. In order to further develop this we will pursue Athena Swan accreditation for all University schools/departments, and advertise this in all FTR JDs, and collect data on FTRs who are o flexible working contracts. | Yes | 2024-06-01 | Athena Swan Working Group responsible for coordinating this. Head of DI, Heads of Schools/ Department Faculty ADRs and Research managers to promote Athena Swan goals. RDC acadmic lead responsible for implementing CEDARS. | Implement a check in HR that information pertaining to flexible working is included in all FTR posts advertised at LJMU. More focussed data collection by HR rto disaggregate those FTRs on flexible working comtracts. Attai Institutiona Silver accrediation for AthenaSWAN and an addition three Bronze departments.
ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health. | Raise awareness for mental health provision via LJMU staff wellbeing hub. Moving forwards we aim to utilise the communication platform provided by the RSA to directly link our FTRs to the LJMU Policy Centre and sign post to other mechanisms of support. | No | 2024-01-01 | OD, RSA and Head of D&I | Track enaggement with online wellbeing hub. Collect data regariding unique hits to this webpage throughiut 2023, and utilise and benchmark data, contonue collection across 2023.
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | LJMU are continually working towards raising awareness of reporting mechnaisms through their AthenaSWAN and broader EDIR work. We aim to utilise the communication platform provided by the RSA to directly link our FTRs to the LJMU Policy Centre and sign post to other mechanisms of support.CEDARS data will interrogate whether RMs and FTRs are aware of these. | No | Summer 2023 and summer 2024 | Athena Swan Working Group responsible for coordinating awareness raising with support from D&I team. RDC acadmic lead responsible for implementing CEDARS. | A minimum of 70% FTRs and RMs are aware of suport and reporting mechanisms for discrimination, bullying and harassment. An increase on data reported in 2022.
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | LJMU are continually working towards raising awareness of reporting mechnaisms through their AthenaSWAN and broader EDIR work. CEDARS data will interrogate whether RMs and FTRs are aware of these. | No | Summer 2023 and summer 2024 | Athena Swan Working Group responsible for coordinating awareness raising with support from D&I team. RDC acadmic lead responsible for implementing CEDARS. | A minimum of 70% FTRs would be confident to raise issues of discrimination, bullying and harassment and a minimum of 70% RMs encourage repoirtin gand addressing incidents of discrimination, bullying and harassment to their research team members.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | Monitor the reporting of discrimination, harassment and bullying by RMs and FTRs. This data is not currently collected so 2023 data will act as benchmark. | No | Summer 2023 and summer 2024 | HR colleagues (data analyst) | Data collected on this outcome, disaggregated by role. 2023 data to act as benchmark.
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | The provision of training packages has been vastly expanded and the introduction of training in relation to principles of EDI also aligns with out AthenaSWAN initiatives. An interactive training package that addresses Equality, Diversity and Inclusion is part of mandatory training and specifically aimed at researchers (including research leaders and managers). | Yes | Annually (Summer 2024) | RMs to encourage completion by FTRs, ADRs/heads of department and research leaders completion by RMs. HR colleagues (data analyst) to rpeort compliance data. | We hope to continue to increase research manager and FTR engagement. Last year, FTRs were 74% compliant, whilst Research Staff (including KTPs) were at 76% compliant and general academic staff 80%. Our aspiration is to record 90% complention rates by summer 2024.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | RSA to ensure that FTRs are given the information about institutional policies and procedures in personalised monthly welcome emails to all new FTRs. | No | 2024-12-01 | OD and RSA to organise session. RMs to encourage engagement with RSA. | RSA to organise at least one annual "Lunch & Learn" session with colleagues from the RSO in relation to funder requirements.
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | Develop a "researcher toolkit" which aims to support, guide & provide resources for all researchers, to enable them to reflect on their own practice, increase consideration of the principles of EDIR in all aspects of their research activities and ensure research integrity.. Specifically, in relation to this action, a guidance documents in relation to reporting and dealing with suspected cases of bad practice or misconduct will be developed and included in this 'toolkit'. RSA to signpost this as part of induction and on a site repository on MS teams platform. | No | Summer 2024 | OD, D&I, Library services, Faculty ADRs, URKEC and Head of Research Excellence | Roll out of the toolkit across LJMU by December 2023 (launched at RKE conference). Numbers of users engaging with toolkit will be evaluated and feedback gathered to refine and improve its effectiveness over time. RSA signpost this document and CEDARS to report that >40% FTRs and RMs understand and are aware of the concordat to support research integrity.
ECM3 | Ensure managers report and address incidents of poor research integrity. | Develop a "researcher toolkit" which aims to support, guide & provide resources for all researchers, to enable them to reflect on their own practice, increase consideration of the principles of EDIR in all aspects of their research activities and ensure research integrity. | No | Summer 2025 | OD, D&I, Library services, Faculty ADRs, URKEC and head of research excellence | Roll out of the toolkit across LJMU by December 2023 (launched at RKE conference). Numbers of users engaging with toolkit will be evaluated and feedback gathered to refine and improve its effectiveness over time. RSA signpost this document and CEDARS to report that >40% FTRs and RMs understand and are aware of the concordat to support research integrity.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | Develop a "researcher toolkit" which aims to support, guide & provide resources for all researchers, to enable them to reflect on their own practice, increase consideration of the principles of EDIR in all aspects of their research activities and ensure research integrity. | No | Summer 2026 | OD, D&I, Library services, Faculty ADRs, URKEC and head of research excellence | Roll out of the toolkit across LJMU by December 2023 (launched at RKE conference). Numbers of users engaging with toolkit will be evaluated and feedback gathered to refine and improve its effectiveness over time. RSA signpost this document and CEDARS to report that >40% FTRs and RMs understand and are aware of the concordat to support research integrity.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | LJMU have an annual research misconduct report, produced by the head of research excellence. Monitor this data and disaggregate to discern reports from FTRs. Also monitor understanding via CEDARS. | No | August 2023 and August 2024 | Head of research excellence and ProVC for RKE | Annual misconduct report communicated and discussed at URKEC at the end of each academic cycle. >50% FTRs to report awareness of the reporting mechanism for research miscondict via CEDARS.
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | The formation of a research staff association (RSA) is currently underway. The RSA will feed into the LJMU Concordat Steering Group (CSG), and members of the RSA will also provide representation of their respective Faculties on Faculty Research and Knowledge Exchange Committee’s, both of which report directly to the University Research and Knowledge Exchange Committee (URKEC). This will give our fixed term research colleagues a voice in strategic meetings that influence LJMU’s research environment and culture. | No | 2023-07-01 | Leadership & Development Foundation (OD), CSG and URKEC colleagues | The SRA will be facilitated by the Learning and Development Foundation (OD) and coordinated, on a voluntary basis, by FTRs themselves. The formaton of the group with Chairs, co-chairs (1 per Faculty) and a co-created terms of reference in place. The set up of an MS Teams site, via whch the RSA will operate, communicate and resoruce share.
ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | RM representation on all relevant committees, as appropriate, with a view to ensuring principles of the condordat and EDI values are considered in relation to all operations and decision making around research environement. | No | 2023-09-01 | URKEC and Faculty ADRs to implement. Guidance provided by RDC academic lead. | RM representation across all Faculty Research and Knowledge Exchange committees, which feed directly into URKEC.
EM5 | Engage with opportunities to contribute to relevant policy development within their institution. | RM and FTR representation on all relevant committees, as appropriate, with a view to ensuring principles of the condordat and EDI values are considered in relation to all operations and decision making around research environement. Relevant issues will feedback in the RSA for discussion and action, where appropriate. | No | 2023-10-01 | URKEC and Faculty ADRs to implement. Guidance provided by RDC academic lead, OD and RSA. | RM and FTR representation across all Faculty Research and Knowledge Exchange committees, which feed directly into URKEC.
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | FTR representation on all relevant committees, as appropriate, with a view to ensuring principles of the condordat and EDI values are considered in relation to all operations and decision making around research environement. Relevant issues will feedback in the RSA for discussion and action, where appropriate. | No | 2023-11-01 | URKEC and Faculty ADRs to implement. Guidance provided by RDC academic lead, OD and RSA. | FTR representation across all Faculty Research and Knowledge Exchange committees, which feed directly into URKEC.
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | Establish, launch and run the RSA, folowing a period of consulation and co-creation of terms of refernce and operational oversight agreement. | No | 2023-09-01 | RDC academic lead, OD, Faculty ADRs, ProVC RKE, URKEC | Launch of RSA, and resultant awareness raising of role as a key stakeholder. FTR representation across all Faculty Research and Knowledge Exchange committees, which feed directly into URKEC.
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | This constitutes another action that supports out progress towards AthenaSWAN charter satus across the institution: LJMU holds the Bronze Athena Swan award which requires the institution to develop, implement and monitor open, transparent and merit-based recruitment. We are working towards our Silver award (August 2023) and will pursue accreditation for all University schools/departments. | No | 2023-09-01 | AthenaSWAN working group, ProVC student experience, D&I team. | LJMU will apply for Institutional AthenaSWAN Silver accrediation, actions for whoch will seek to improve community and culture across the institution, incuding in research spaces.Specifically in relation to recruitment, we hope that merit based recruitment will diversify applications and colleagues. Further, we aim to streamline actions across several equality initiatives (Athena Swan, Race Equality Charter, and the Concordat). This will open dialogue between respective leads will avoid the duplication of efforts and make this work more efficient for colleagues.
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | LJMU have a standardised approach to induction that applies centrally and at local level Inductions. However, data is not captured currently specific to FTRs. | Yes | 2024-01-01 | HR (data analyst) | HR to monitor the numbers of Inductions taking place for FTRs, and formally report to Faculty RKE committees and URKEC.
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | As part of the development of the Faculty Brochures and research toolkits, we will include information about the institutional and local research strategy, the individual’s role within that strategy, support and career development opportunities, including appraisal and promotion. These documents will advocate for engagement with CEDARS and set out the University’s commitment to the Principles of the Concordat to Support the Career Development of Researchers. Data from CEDARS completion in 2022 revelaed that LJMU currently employs n=128 Research-only staff. 22 R-only staff completed CEDARS = 17%. | Yes | 2024-01-01 | HR responsible for implementation; RDC lead responsible for ensuring CEDARS is implemented. | Completion rate for CEDARS to exceed the sector benchmark by achieving 35% completion amongst FTRs. >50% (our current benchmark) FTRs to express that promotion is transparent and merit based in CEDARS.
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers. | See actions EI1 and EI3 in relation to open, transparent and merit based recuitment. | No | 2024-01-01 | As above | Institutional AthenaSWAN accreditation, and asscoauated changes this would bring to be captured in CEDARs. Completion rate for CEDARS to exceed the sector benchmark by achieving 35% completion amongst FTRs.
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | Raise awareness amongst RMs of the opportunity to include in their grant proposals the appropriate funding to support the promotion of the FTR, where appropriate and eligible, working on the grant. Collect data on RMs awareness of costing for FTR developement in research grants via CEDARS. | No | 2024-06-01 | RSO. RDC academic lead to implement CEDARS. | Enhance PIs understanding and working out of ‘Full Economic Costing’ to take into account research staff promotion where appropriate and eligible. >30% RMs aware of costing for FTR development in research grants.
ER1 | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder. | RSA to ensure that FTRs are given the information about institutional policies and procedures in personalised monthly welcome emails to all new FTRs. | No | 2023-10-01 | RSA and OD | RSA to organise at least one annual "Lunch & Learn" session with colleagues from the RSO in relation to funder requirements.
ER2 | Researchers understand their reporting obligations and responsibilities. | Establish a formnal process, by which, RMs can monitor dissemination and implementation of the agreed 10 days of development activity for FTRs | No | 2024-12-01 | OD, HR | Develop this monitoring technique in 2023 with a view to launch in 2024. 2024 data to act as benchmark.
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | Institution, faculties and schools to widely promote and encourage engagement with centrally available opportunities to develop leadership skills such as ILM coaching and mentoring and ILM Leadership qualifications. | No | 2023-10-01 | OD, ADRs, heads of school, research group leaders, ProVC RKE | Monitor the number of staff with research management resonsiblity taking up these opportunities. Utilise 2023 as benchmark data and look to increase participation thereafter.
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | Roll out gold standard guidance document and training for RMs on carrying out PDRs for FTRs to ensure they provide a comprehensive, clear and fair PDR. | No | 2024-03-01 | HR recruitment colleagues, with support from OD, D&I and RDC academic lead | >60% FTRs reporting a positive experience of PDPRs, building on our current benchmark of 50%.
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | See EI4: Institution, faculties and schools to widely promote and encourage engagement with centrally available opportunities to develop leadership skills such as ILM coaching and mentoring and ILM Leadership qualifications. | No | 2023-10-01 | OD, ADRs, heads of school, research group leaders, ProVC RKE | Monitor the number of staff with research management resonsiblity taking up these opportunities. Utilise 2023 as benchmark data and look to increase participation thereafter.
EM4 | Managers actively engage in regular constructive performance management with their researchers. | See EI5: Roll out gold standard guidance document and training for RMs on carrying out PDRs for FTRs to ensure they provide a comprehensive, clear and fair PDR. This guidance will encourage engagement in pre-post- PDPR meetings/reviews. | No | 2024-03-01 | HR recruitment colleagues, with support from OD, D&I and RDC academic lead | >60% FTRs reporting a positive experience of PDPRs, building on our current benchmark of 50%.
ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | FTRs to provide details within written documentation in support of PDPR reflecting on key achievements and highlighting any barriers to the achievement of objectives, as part of their PDPR process. | No | 2024-01-01 | HR | >80% of FTRs completed their PDPR, building on our current benchmarl of 77%.
Job security
The aim of this obligation is to improve the job security of researchers.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | See ECM4 regarding how the LJMU seek to promote flexible working offer to enhance and promote flexible working options to attract, retain and enable FTRs. | Yes | 2024-06-01 | Athena Swan Working Group responsible for coordinating this. Head of DI, Heads of Schools/ Department Faculty ADRs and Research managers to promote Athena Swan goals. RDC acadmic lead responsible for implementing CEDARS. | Implement a check in HR that information pertaining to flexible working is included in all FTR posts advertised at LJMU. More focussed data collection by HR to disaggregate those FTRs on flexible working comtracts. Attain Institutiona Silver accrediation for AthenaSWAN and an addition three Bronze departments.
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | Local research group meetings, school level staff forums and Faculty forums to encourage FTRs to enhance professional development and promote the concordat recommendation of up to 10 days spent on personal development. This should also be acknowledged and discussed in PDPRs. Participation to be monitored via CEDARS. | No | Summer 2024 | Research group leads, heads of School, ADRs, PVCs | The percentage of FTRs completing in 10 days op CPD to reach at least 20%, building significantly on the current benchmark of 5%.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | Our well established and award winning ACTivator series is currently under review in response to the detailed evaluation, analysis performed and resultant recommendations generated. This is in terms of both content and delivery. The new, evolved packages will be launched and communicated in 2023. | No | 2023-09-01 | OD, RSA and RDC academic lead to implement CEDARS | >40% OF FTRs to engage with ACTivtaor series, current benchmark. Continue to collect feedback data that will inform further development in repsonse to the needs of FTRs.
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | See PCD1: Local research group meetings, school level staff forums and Faculty forums to encourage RMs to enhance professional development and promote the concordat recommendation of up to 10 days spent on personal development for their FTRs. This should also be acknowledged and discussed in PDPRs. Participation to be monitored via CEDARS. Also see EM1 regarding research leadership training for RMs. | No | Summer 2024 | Research group leads, heads of School, ADRs, PVCs | The percentage of FTRs completing in 10 days op CPD to reach at least 20%, building significantly on the current benchmark of 5%.
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | Our 2022 implementation data revealed that leadership training does not seem to have been prioritised by FTRs. Narrative around research leadership training should be woven into PDPRs and captured during goal setting. This should also be repeatedly emphasised by the RSA. | No | 2024-06-01 | Research group leads, ADRs, RMs | The percentage of FTRs completing in 10 days op CPD to reach at least 20%, building significantly on the current benchmark of 5%.
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | LJMU provide an e-learning module for all managers 'Appraisals and Connected Conversations'. The Appraisal online session is currently a non-mandatory session, that to date has been completed by 35% of RMs and 34% of fixed term researchers. Moving forward, we intend to make attendance at the appraisal online session mandatory for RMs. | Yes | Review annually, Dec 2023. Implement CEDARS Spring 2024 | HR, OD, ProVC RKE, ADRs, local research group leads | As a minimum we expect >60% of RMs to engage in these activities, increasing to 70% in 2024. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews. | See PCDI6: Our well established and award winning ACTivator series is currently under review in response to the detailed evaluation, analysis performed and resultant recommendations generated. This is in terms of both content and delivery. The new, evolved packages will be launched and communicated in 2023. | No | 2023-09-01 | OD, RSA and RDC academic lead to implement CEDARS | >40% OF FTRs to engage with ACTivtaor series, current benchmark. Continue to collect feedback data that will inform further development in repsonse to the needs of FTRs.
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually. | See PCDI2: LJMU provide an e-learning module for all managers 'Appraisals and Connected Conversations'. The Appraisal online session is currently a non-mandatory session, that to date has been completed by 35% of RMs and 34% of fixed term researchers. Moving forward, we intend to make attendance at the appraisal online session mandatory for RMs. See EI5: Roll out gold standard guidance document and training for RMs on carrying out PDRs for FTRs to ensure they provide a comprehensive, clear and fair PDR. | Yes | Review annually, Dec 2023. Implement CEDARS Spring 2024 | HR, OD, ProVC RKE, ADRs, local research group leads | As a minimum we expect >60% of RMs to engage in these activities, increasing to 70% in 2024. We will collect robust pre and post evaluation data to understand the outcomes of these sessions. We will further explore awareness and outcomes via CEDARS. >60% FTRs reporting a positive experience of PDPRs, building on our current benchmark of 50%.
PCDR4 | Researchers positively engage in career development reviews with their managers. | See PCDI2: LJMU provide an e-learning module for all managers 'Appraisals and Connected Conversations'. The Appraisal online session is currently a non-mandatory session, that to date has been completed by 35% of RMs and 34% of fixed term researchers. Furthermore, the CSG support mandatory PDPRs. | Yes | Review annually, Dec 2023. Implement CEDARS Spring 2024 | HR, OD, ProVC RKE, ADRs, local research group leads | CEDARS data reveal that 50% of FTRs who participated in an annual appraisal found it a useful and meaningful process and of those that did not complete it was due to being a relatively new starter. >80% of FTRs completed their PDPR, building on our current benchmarl of 77%.
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | The current booking system in use for OD led training records total n of attendees and does not provide information on % of a specific population in LJMU. CRN system is due to be launched in September 2023 and will collect much more comprehensive data regarding % attendees and also protected characteristics (see also PCDI6). See additionally PCDM2 and PCDM4 for actions related to researchers’ support in exploring and preparing for a diversity of careers and use of the 10 development days. | Yes | 2023-09-01 | OD and HR | The new booking system wil enable the collection of much more comprehensive data regarding % attendees and also protected characteristics at OD led training. Not only will this provide further context to FTRs but also disaggregate these data by protected characteristics and enable LJMU to determine any potential discrepencies in attendance based on these, that could feed into AthenaSWAN actions.
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | Ensure LJMU Symplectic database is up to date. Consider and develop professional career development plan through appraisals and the use of the Vitae Wheel. | Yes | 2024-01-01 | FTRs and RMs | 100% of staff to have an appraisal. 100% of staff will report Symplectic being up to date.
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | OD will continue to provide opportunities for FTRs to develop broader leadership skills, raisied in PDPR with RMs. This will be encouraged further via the newly established RSA. Only 5% FTRs completed leadership training with OD. although 35% of FTRs expressed a desire to complete these, 40% RS understood the importance of developing a research identity, and in comination with actions PCDI1, PCDM3 and PCDI2 to increase days spent on CPD activity, we hope for an increase in FTR engagement. | No | 2025-01-01 | OD, RMs | >40% of FTRs to engage with ACTivtaor series, current benchmark. Continue to collect feedback data that will inform further development in repsonse to the needs of FTRs. >40% of FTRs to engage in leadership training.
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours. | In addition to PCDM3 and PCD1, local research group meetings, school level staff forums and Faculty forums to encourage RMs to support activity that enhances research identity of their FTRs. Participation to be monitored via CEDARS. Also see EM1 and PCDI4 regarding research leadership training for RMs. | No | Summer 2024 | Research group leads, heads of School, ADRs, PVCs. RDC academic lead to implenent CEDARS. | The percentage of FTRs completing in 10 days op CPD to reach at least 20%, building significantly on the current benchmark of 5%. >45% of FTRs to report that they have time to develop their research identity and >50% to report that thie RM is supportove of this. These figures build on current benchmarks.
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | See EI4: Institution, faculties and schools to widely promote and encourage engagement with centrally available opportunities to develop leadership skills such as ILM coaching and mentoring and ILM Leadership qualifications. CEDARS will evauate the imact of this. | No | 2023-10-01 | OD, ADRs, heads of school, research group leaders, ProVC RKE | Monitor the number of staff with research management resonsiblity taking up these opportunities. Utilise 2023 as benchmark data and look to increase participation thereafter. >50% FTRs to report that their RM is suportive of CPD activity.
PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills | OD will continue to provide opportunities for FTRs to develop broader leadership skills, raisied in PDPR with RMs. This will be encouraged further via the newly established RSA. Only 5% FTRs completed leadership training with OD. although 35% of FTRs expressed a desire to complete these, 40% RS understood the importance of developing a research identity, and in comination with actions PCDI1, PCDM3 and PCDI2 to increase days spent on CPD activity, we hope for an increase in FTR engagement. | No | 2025-01-01 | FTRs, OD, RMs | >40% of FTRs to engage with ACTivtaor series, current benchmark. Continue to collect feedback data that will inform further development in repsonse to the needs of FTRs. >40% of FTRs to engage in leadership training.
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | We will commit to exploring the development of an interactive workshop for employers/researchers to liaise with employers to provide job opportunities. We are aware of examples across the sector (e.g. University of Liverpool's Prosper Workshop) and will learn from these to explore the possibility of developing a bespoke workshop for our research community, with a focus on fixed-term researchers. | Yes | 2024-06-01 | ProVC RKE, OD, RDC academic lead and RSA | The development and delivery of a workshop with attendance from at least 40% of staff on fixed-term research contracts. Experiences of this will be captured via pre and post monitoring and engagement with attendees.
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | The ACTivator series is currently under review in response to the detailed evaluation, analysis performed and resultant recommendations generated. This is in terms of both content and delivery. The new, evolved packages will be launched and communicated in 2023. We will deliver, evaluate and continue to review the ACTivator programme with specific promotion to the managers of FTRs. This will include data specific to the Concordat cohort (see Action PCD16). We will engage RMs with CEDARS in 2023/4 to explore implementation and outcome data. | Yes | 2023-09-01 | OD, RMs, local research leads and ADRs. The RSA to communicate also. | Increased researcher engagement with development activities, specifically core ACTivator workshops with 75% of RMs and FTRs attending at least one workshop per academic year. Completion rate for CEDARS to exceed the sector benchmark by achieving 35% completion amongst FTRs.
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | FTRs will engage with OD and new version of ACTivator opportunities and actively engage with their mentors. Furthermore, a HR booking system will be launched to enable more thorough data collection and reporting. | No | 2023-09-01 | HR and OD | In line with PCDI6 and PCDM2, we will collect data specific to FTRs to monitor engagement with the OD and ACTivator provision that is available to staff. The current booking system in use records total n of attendees and does not provide information on % of a specific population in LJMU. CRN system is due to be launched in September 2023 and will collect much more comprehensive data regarding % attendees and also protected characteristics, which will only be utilised for reporting group level statistics.
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation. | Continue to run the University’s Research and Knowledge Exchange celebration with continued involvement from the CSG in the design, planning and running of the event as well as an opportunity for awareness raising activity. Active involvement from the RSA will also be facilitated. Establish robust measures to evaluate outcomes and satisfaction. | No | 2023-12-01 | FTRs, ProVC RKE, ADRs | Implement a robust evaluation to identify the outcomes of engagement for researchers in these activities.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | https://www.ljmu.ac.uk/ris/concordat?utm_medium=301_Redirect&utm_source=/about-us/structure/professional-services/research-and-innovation-services/concordat |  |  |  | ADR | Assoiate Dean for Research
2 | https://www.ljmu.ac.uk/ris/concordat/2019-revised-concordat |  |  |  | CAP | Concordat Action Plan
3 | https://www.ljmu.ac.uk/ris/concordat/statement-of-expectations |  |  |  | CEDARS | The Culture, Employment and Development in Academic Research Survey
4 | https://www.ljmu.ac.uk/ris/concordat/concordat-steering-group |  |  |  | CSG | Concordat Steerng Group
5 | https://www.ljmu.ac.uk/ris/concordat/research-staff-association |  |  |  | FTR | Fixed Term Researcher
6 | https://www.ljmu.ac.uk/ris/concordat/development-activity-guidance |  |  |  | HR | Human Resources
7 | https://www.ljmu.ac.uk/ris/concordat/relevant-documents |  |  |  | ILM | The Institute of Leadership & Management
8 | https://www.ljmu.ac.uk/ris/concordat/frequently-asked-questions |  |  |  | OD | Leadership and Development Foundation
9 |  |  |  |  | LJMU | Liverpool John Moores University
10 |  |  |  |  | ProVC | Pro Vice Chancellor
11 |  |  |  |  | RDC | Researcher Development Concordat
12 |  |  |  |  | RKE | Research and Knowledge Exchange
13 |  |  |  |  | RM | Research Manager
14 |  |  |  |  | RS | Research Staff Association
15 |  |  |  |  | URKEC | University Research and Kowledge Excahnage Committee
16
17
18
19
20

## Funders' obligations
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions
Employment
Job security
The aims of these obligation are to improve the job security of early career researchers.
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to do so.
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Guidance
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: | Enter relevant information |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | Enter relevant information |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | Enter relevant information |  |  |  | Research staff |  |  | These are your primary beneficiaries, and should be prioritised across the action plan - both by being targeted with actions and evaluated through success measures.
| Institutional context: | Enter relevant information that helps frame the action plan and the intended institutional audience. For example, this box can be used to disclose the research intensiveness of the institution, providing a justification for the breadth/depth of the actions disclosed. |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Describe here your actions/interventions for meeting the obligation, referring to actions elsewhere in the action plan if preferred. | Has the action been carried forward from a previous action plan? "yes" / "no" | Indicate a month and year | Name all key parties responsible for the action(s) and success measure(s) | Describe here your success measure(s), used to report against the intended impact for researchers and incorporating researchers' views wherever possible. | Describe here any supplementary information. | Describe here a written summary of the progress made against the obligation, taking a broad view of the people and/or organisational development that may have occurred. | Provide evidence that directly reports against all success measures described previously. | Indicate the next steps for the action from the following options: "ongoing" (if the deadline is scheduled in the future), "carried forward" (if the action was not completed as planned by the initial deadline) or "no further action" (accompanied by a brief explanation).
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | Institutions planning actions for specific funders' obligations can insert these obligations into the relevant section of the institution template.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | Use these spaces to provide links and references for information provided in the action plan. |  |  |  |  | Use these spaces to describe abbreviations and
2 | [5 empty] | terms used in the action plan.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
N.B. This section is for reporting only, and should not be completed prior to the beginning of the action plan's term.
For brevity, the remaining obligations have been omitted from this 'Guidance' sheet.

## Tips
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff |  |  | Only include institutional audiences considered to directly benefit from the action plan, remembering that research staff should be prioritised.
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers. Our internal evaluation revealed that researchers feel the university strategic priorities do not reflect their own (62% in a consultation said that they felt disconnected from the university's recent 'Strategy 2030'). Heads of Faculties also report from conversations at committee meetings that researchers feel the university's strategic priorities are not entirely aligned with the reality felt in specific research disciplines. Optional: Institutions can use this space (if desired) to discuss the context that frames the actions and success measures disclosed.
ECI1 | Ensure all relevant staff are aware of the Concordat
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | Providing actions for every obligation is not mandatory, although action plans should aim to target those in their priority areas and/or those highlighted by researchers during the internal evaluation.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Host programme of Faculty- and institution-wide workshops on research culture, capturing local and broader views on key themes in research and reflecting these with the institution's 'Strategy 2030' priorities. Gather a comprehensive range of anonymous views from research staff on how they feel their Faculty research environment compares to the institution as a whole through quarterly Faculty pulse surveys. | no yes | Jul-23 Being specific (rather than only stating "ongoing" or "annually") indicates that reporting has been properly scheduled and that actions are timebound. May-23 | • RCWG • Heads of Faculties • PVC-RI • Faculty-HR • RCWG Broad and specific responsibility can show a joined-up approach to working, connects institutional stakeholders around the Researcher Development Concordat and also shares the workload. | • Host quarterly workshops for each Faculty, and biannual institutional workshops. Success measures like this (i.e., "action completed") are acceptable but should be complemented by other measures that show the impact of the action. • Drafting of workshop reports led by research staff attendees, and reports instated as a standing agenda item at Faculty committee meetings. • At least 30 research staff attendance (on average) at Faculty workshops. Positive post-event feedback from at least 80% of research staff attendees. • At least 40% of research staff (on average) across all 5 Faculties respond to Faculty pulse surveys. Success measures like these allow institutions to qualitatively and quantitatively assess progress against the obligation. Note the words underlined in the obligation and consider how the success measures could align with these. Setting numerical (i.e., SMART) targets can provide an unambiguous benchmark to report progress against in the future. |  | Programme of workshops conducted digitally due to ongoing COVID restrictions (1). Attendance was encouraging, with a good number of research staff joining and contributing to both discussions and the chat function. Research staff were less engaged in the reporting of the workshops than hoped, partially attributed to the less stimulating setting of online events. Feedback from research staff attendees was very positive, and both this feedback and the workshop discussion points were fed into Faculty committee meetings. In one instance, this prompted a Head of Faculty to set up focus groups to explore one particular issue more closely. Faculty pulse survey engagement was encouraging, albeit variable across the Faculties. The findings and trends will help inform future Concordat action plans and the university's Research Culture manifesto. By describing the action's progress in narrative form, institutions can explain success in greater detail, or mitigate challenges experienced, by providing helpful contextual information. | • All 5 Faculties' workshops held quarterly, as well as two workshops held at an institutional level. • Workshop reporting only partially led by research staff across the Faculties. All Faculty committees successfully instated research culture reports as an agenda item. • 34 research staff attended each workshop on average. 86% of research staff attendees gave positive post-event feedback, with 84% saying they "found the workshop to be helpful". • 38±3% of research staff responded to pulse surveys across all Faculties, although some only received 35% research staff response rates. Ensuring you report against all success measures provides a better assessment of the impact achieved and shows commitment to researchers that the institution cares about their views and behaviour. | no further action (action now considered normal business) After selecting from one of the set responses in the column header, institutions can briefly indicate the rationale for this decision (e.g., "action successfully embedded" or "action delayed, partially completed").
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Even if no action is intended/needed, it is encouraged to include success measures that show how different stakeholders engage with/benefit from other actions. |  | Jul-23 | • RCWG | At least 70% of research staff answering CEDARS q42.4 ("feel included in your immediate research environment/group") agree or strongly agree (CEDARS 2021: 62%) | Survey response rate in 2021: 16% research staff (n=147) Optional: This space can be used to provide details not suitable for the other columns. For example, you can add information relevant to an action and/or a success measure to help demonstrate feasibility. | CEDARS response rate improved considerably after a campaign of targeted communications. This coincided with less positive responses for q42.4 than anticipated, suggesting that the university is now successfully reaching a previously 'silent' yet dissatisfied group of research staff with the survey. | 64% of research staff responded agree/strongly agree for CEDARS q42.4. 22% of all research staff (n=202) responded to CEDARS.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and Supplementary Information (more rows can be added) |  |  |  |  | Abbreviations and Glossary (more rows can be added)
1 | www.university.ac.uk/researchculture/researchcultureworkshops/summary |  |  |  | PVC-RI | Pro-Vice Chancellor for Research & Innovation
2 | Using these spaces can help keep the main body of the action plan as concise as possible. |  |  |  | RCWG | Research Culture Working Group
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
This sheet gives a hypothetical response to a group of obligations under Environment and Culture > Awareness and engagement.
Tips and advice are shown alongside to highlight how to organise actions and success measures to deliver the most impact, as well as to demonstrate a transparent and compelling approach to reporting on progress and the original success measure.
For brevity, the remaining obligations have been omitted from this 'Tips' sheet.